## FAFSA Simpl Action Plan
FAFSA Simplification Action Plan Template
Category | Sub-Category or Audience | Task Description | Status | Dependencies | Project Health | State Agency or College Responsible | Office/Unit/Dept Responsible | Office/Unit/Dept Accountable | Office/Unit/Dept Consulted | Office/Unit/Dept Informed | Start Date | End Date | Comments | Resources
Campus Administration (Presidents, VP's and other decision makers) | Key Decision | Designate a campus co-champion to work with Financial Aid director | Not started | None |  | TBD
|  | Decision regarding closing financial aid offices for dedicated processing times | Not started |  |  | TBD
|  | Decisions regarding expedited hiring to fill vacant financial aid positions | Not started |  |  | TBD
|  | Decision regarding authorizing overtime | Not started |  |  | TBD
|  | Decision regarding incentives for financial aid staff who stay on | Not started |  |  | TBD
|  | Decision regarding the use of SBCTC standard awarding methodology | Not started |  |  | TBD
|  | Decision regarding campus access to FAFSA information | Not started |  |  | TBD | [7 empty] | https://fsapartners.ed.gov/sites/default/files/attachments/2024-01/2023FSAConfSessionBO10DataUseConsiderationUnderFutureFAFSA_Final.pdf
|  | Decision regarding access to FTI information | Not started |  |  | TBD | [7 empty] | https://www.irs.gov/pub/irs-pdf/p1075.pdf
|  | Decision regarding the use of third party to support financial aid process | Not started |  |  | TBD
|  | Decision regarding annual leave exceeding annual limit | Not started |  |  | TBD
|  | Decision regarding dedicated training time for financial aid staff | Not started |  |  | TBD
|  | Redeployment of staffing from other departments to support financial aid front desk customer services | Not started |  |  | TBD
|  | Decision on drop for non-payment dates | Not started |  |  | TBD
|  | Increase in temporary financial aid staffing | Not started |  |  | TBD
|  | Decision on the use of mass packaging | Not started |  |  | TBD
|  | Decision to replace lost pell grant funds with institutional or foundation funds | Not started |  |  | TBD
|  | Decision regarding availability and distribution of emergency aid | Not started |  |  | TBD
Campus Advising Partners (Outreach, Advising, etc.) | Training Resources | 2024-25 FAFSA Form Preview Presentation | Not started |  |  | TBD | [7 empty] | https://fsapartners.ed.gov/knowledge-center/library/application-processing/2023-07-31/2024-25-fafsa-form-preview-presentation
|  | FAFSA Changes FAQ Webpage | Not started |  |  | TBD | [7 empty] | https://financialaidtoolkit.ed.gov/tk/announcement-detail.jsp?id=fafsa-changes-faqs
|  | Understanding the new FAFSA Submission Summary | Not started |  |  | TBD | [7 empty] | https://www.youtube.com/watch?v=jHaAtCMmB2c
|  | How to Compare Financial Aid Offers and Schools | Not started |  |  | TBD | [7 empty] | https://www.youtube.com/watch?v=puPi3DPNMDw
|  | Why Should I Complete the 24/25 FAFSA Form | Not started |  |  | TBD | [7 empty] | https://www.youtube.com/watch?v=U2FkQ_KxQRI
|  | Special Student Populations and Circumstances for 2024-25 FAFSA Form Webinar | Not started |  |  | TBD | [7 empty] | https://www.youtube.com/watch?v=zpGjs4yg1z8&t=2078s
|  | May 2023 ¦ FAFSA Changes: An Overview | Not started |  |  | TBD | [7 empty] | https://www.youtube.com/watch?v=kSHQmtSQFvo&list=PLyCvB-1-qvl8RaytPnfFbpbXRrhXpkmwh&index=3
|  | August 2023 ¦ College Access Professionals 2024-25 FAFSA Demonstration | Not started |  |  | TBD | [7 empty] | https://www.youtube.com/watch?v=k26QnHn7Xcs&list=PLyCvB-1-qvl8RaytPnfFbpbXRrhXpkmwh&index=4
|  | FAFSA Overview Fact Sheet | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://financialaidtoolkit.ed.gov/resources/fafsa-changes-overview.pdf
|  | October 2023 ¦ Financial Aid Bootcamp: How to Prepare for the 2024-25 FAFSA Form | Not started |  |  | TBD | [7 empty] | https://www.youtube.com/watch?v=Fao1ZwhN_no
|  | October 2023 ¦ Financial Aid Bootcamp: Dependent Student 2024-25 Prototype Preview | Not started |  |  | TBD | [7 empty] | https://www.youtube.com/watch?v=EqpZ45wIzkc
|  | October 2023 ¦ Financial Aid Bootcamp: Independent Student 2024-25 Prototype Preview | Not started |  |  | TBD | [7 empty] | https://www.youtube.com/watch?v=GBhikcNFYvM
|  | December 2023 ¦ 2024-25 FAFSA Contributor Prep | Not started |  |  | TBD | [7 empty] | https://www.youtube.com/watch?v=JZUBlw1b7_I
|  | February 2024 ¦ Parent Guide to Federal Financial Aid | Not started |  |  | TBD | [7 empty] | https://www.youtube.com/watch?v=2fdXF6IXpbw
|  | Adult Student FAQ | Not started |  |  | TBD | [7 empty] | https://financialaidtoolkit.ed.gov/tk/outreach/target/adults.jsp
|  | Parent FAQ | Not started |  |  | TBD | [7 empty] | https://financialaidtoolkit.ed.gov/tk/outreach/target/parents.jsp
|  | Counselors and Mentors Handbook on Federal Student Aid | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://financialaidtoolkit.ed.gov/resources/2024-25-counselors-handbook.pdf
|  | Federal Student Aid Handbook Glossary | Not started |  |  | TBD | [7 empty] | https://fsapartners.ed.gov/knowledge-center/fsa-handbook/glossary
|  | Make a Financial Aid Presentation | Not started |  |  | TBD | [7 empty] | https://financialaidtoolkit.ed.gov/tk/outreach/presentation.jsp
|  | FAFSA Submission Summary Sample (English) | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://financialaidtoolkit.ed.gov/resources/2024-25-fafsa-submission-summary-sample.pdf
|  | FAFSA Submission Summary Sample (Spanish) | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://financialaidtoolkit.ed.gov/resources/2024-25-fafsa-submission-summary-sample-spanish.pdf
|  | FAFSA PDF (English) | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://studentaid.gov/sites/default/files/2024-25-fafsa.pdf
|  | FAFSA PDF (Spanish) | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://studentaid.gov/sites/default/files/2024-25-fafsa.pdf
|  | 2024-25 FAFSA Frequently Asked Questions | Not started |  |  | TBD | [7 empty] | https://fsapartners.ed.gov/knowledge-center/topics/fafsa-simplification-information/2024-25-fafsa-frequently-asked-questions
|  | How To Submit the 2024–25 FAFSA® Form if Your Contributor Doesn’t Have an SSN | Not started |  |  | TBD | [7 empty] | https://studentaid.gov/announcements-events/fafsa-support/contributor-social-security-number
|  | What should I do if I have an unusual circumstance and can’t provide parent information? | Not started |  |  | TBD | [7 empty] | https://studentaid.gov/help/unusual-circumstances
|  | 2024–25 FAFSA® Help | Not started |  |  | TBD | [7 empty] | https://studentaid.gov/apply-for-aid/fafsa/filling-out/help
|  | Filling Out the FAFSA® Form | Not started |  |  | TBD | [7 empty] | https://studentaid.gov/apply-for-aid/fafsa/filling-out
|  | 7 Key Changes Coming to the 2024–25 FAFSA® Experience | Not started |  |  | TBD | [7 empty] | https://studentaid.gov/articles/fafsa-changes-coming/
|  | 10 Common FAFSA Mistakes To Avoid | Not started |  |  | TBD | [7 empty] | https://studentaid.gov/articles/10-fafsa-mistakes-to-avoid/
|  | 9 Myths About the FSA ID | Not started |  |  | TBD | [7 empty] | https://studentaid.gov/articles/9-myths-fsa-id/
|  | 8 Easy Steps for Parents Completing the 2023–24 FAFSA® Form | Not started |  |  | TBD | [7 empty] | https://studentaid.gov/articles/fafsa-for-parents/
|  | Explainer: How to Get an FSA ID without a Social Security Number | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/FSA_ID_without_SSN.pdf
|  | Spanish Explainer: How to Get an FSA ID without a Social Security Number | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/Spanish_FSA_ID_without_SSN.pdf
|  | FAFSA Simplification Brief for Campus Partners | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/FAFSA_Simplification_Brief_Campus_Partners.pdf
|  | Tip Sheet for Adult Learners | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/2023-24_Tip_Sheet_Adult_Learners.pdf
|  | Tip Sheet for Financial Aid Administrators Working with Refugee and Asylee Students | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/Tip_Sheet_FAA_Refugee_Asylee_Students.pdf
|  | Tip Sheet for Servicemembers and Veterans | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/2023-24_Tip_Sheet_Servicemen_Veterans.pdf
|  | Eligibility for Students With Criminal Convictions | Not started |  |  | TBD | [7 empty] | https://studentaid.gov/understand-aid/eligibility/requirements/criminal-convictions
|  | Tip Sheet for Unaccompanied Homeless Youth (UHY) | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/Tip_Sheet_for_Unaccompanied_Homeless_Youth.pdf
|  | Tip Sheet for Undocumented Students | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/2023-24_Tip_Sheet_Undocumented_Students.pdf
| Outreach Partners Campus Talking Points | Campus Financial Aid Deadline/Priority Date | Not started |  |  | TBD
|  | Campus message regarding Financial Aid Office closures | Not started |  |  | TBD
|  | Campus message regarding financial aid distribution dates | Not started |  |  | TBD | Financial Aid |  |  | Campus Partners
|  | Campus message regarding access to emergency aid | Not started |  |  | TBD
|  | Message regarding FAFSA simplification | Not started |  |  | TBD
|  | Talking points regarding financial aid distribution delays | Not started |  |  | TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
Bursars Office |  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
TBD
Financial Aid Office Processes, policies and procedures | Forms | Create Consent to Release FTI | Not started |  |  | TBD
|  | Create Housing Option Form | Not started |  |  | TBD
|  | Create form for enrollment level with enrollment intensity | Not started |  |  | TBD
TBD
| Technology | Enroll with a new FTI Mailboxes | Not started |  |  | TBD
|  | Install new EdConnect (8.6.1) | Not started |  |  | TBD
TBD
TBD
TBD
| FTI Security | Gain Access/update Query Security | Not started |  |  | TBD
|  | Update Security Access to ISIR Data pages | Not started |  |  | TBD
|  | Update Security Access To WCG screens | Not started |  |  | TBD
|  | Coordinate with Workforce Funding Programs to update/create policies - possibly can work with SBCTC, Jennifer Dillinger | Not started |  |  | TBD
|  | District campuses - Assess SACR and roles in security | Not started |  |  | TBD
|  | Create policy for assessing eligibility for other programs, ex. Trio | Not started |  |  | TBD
| Enrollment Intensity | Implement for Federal Aid | Not started |  |  | TBD
|  | Implement for State Aid | Not started |  |  | TBD
|  | Review SAP Policy for Impacts/Implications | Not started |  |  | TBD
|  | Review FLF Indicators Processes | Not started |  |  | TBD
TBD
TBD
TBD
| Item Types | Emergency Grants: Modify and/or Create new item types to no longer count against COA against award | Not started |  |  | TBD
|  | Update Passport Incentive Item Type to allow for emergency awarding | Not started |  |  | TBD
TBD
TBD
| ISIR Comment Code Revisions and impact to jobset processes | Create Process for Rejected/Provisional Independent FAFSAs | Not started |  |  | TBD
|  | Review Checklists for Revisions/Updates | Not started |  |  | TBD
TBD
TBD
| Budgets | Add Budget Item to include licensing fees Required for Programs | Not started |  |  | TBD
|  | Determine housing selection criteria or default | Not started |  |  | TBD
|  | Update Webpage/Forms to include language for students who may need to switch housing option (see Forms above) | Not started |  |  | TBD
TBD
TBD
| WSAC Updates | Update SAP to align with new regulations | Not started |  |  | TBD
|  | Review Enrollment Intensity Impacts to policies | Not started |  |  | TBD
|  | Fix Cruncher/Eligibility Checker | Not started |  |  | TBD
|  | Review/Prepare Interim impacts on reporting due to FTI Data Restrictions | Not started |  |  | TBD
TBD
| Procedure Updates | Update/Review SAP Procedures | Not started |  |  | TBD
|  | Update/Review R2T4 Procedures | Not started |  |  | TBD
|  | Update File Review Process (examples: HS diploma/GED, Legal Guardianship, citizenship, Emancipated Minor, loan bankruptcy, SSN confirmation, unusual enrollment, Fresh Start, etc.) | Not started |  |  | TBD
|  | Update Awarding Policy/Packaging Plans | Not started |  |  | TBD
|  | Appeal/Professional Judgement | Not started |  |  | TBD
|  | Review Daily Processes For Impacts | Not started |  |  | TBD
|  | Review Policy on Treatment of number in college, number in household | Not started |  |  | TBD
|  | Review Policy on Treatment of small businesses/family farms | Not started |  |  | TBD
|  | Update Awarding parameters for new definition of other financial aid and exclusions from that definition, like emergency aid | Not started |  |  | TBD
|  | Consider Replacing lost Pell grants with institutional dollars | Not started |  |  | TBD
|  | Consider Replacing lost state grants with institutional dollars | Not started |  |  | TBD
|  | Identify Process to Convert negative SAI to zero for awarding purposes | Not started |  |  | TBD
|  | Review changes to 2024-25 verification requirements | Not started |  |  | TBD
|  | Consider How to Account for no SAI proration for periods of enrollment other than 9 months | Not started |  |  | TBD
|  | Establish Data use/sharing Policies | Not started |  |  | TBD
|  | Update/Review SEOG awarding guidelines | Not started |  |  | TBD
|  | Enact Required Changes to COA Components | Not started |  |  | TBD
|  | Update Staff Access for change from CPS to Partner Portal | Not started |  |  | TBD
TBD
Financial Aid Office Training | Financial Aid Staff Training | Data Use and Considerations Under the FUTURE Act and FAFSA® Simplification Act | Not started |  |  | TBD | Financial Aid | None | None | Campus Partners |  |  |  | https://www.youtube.com/watch?v=XTaHoIBW2k0&t=41s
|  | FAFSA Simplification Application and Need Analysis | Not started |  |  | TBD | Financial Aid |  |  | Campus Partners |  |  |  | https://www.youtube.com/watch?v=JY7YBLZ8qeA&t=2s
|  | Calculating a Federal Pell Grant | Not started |  |  | TBD | Financial Aid |  |  | Campus Partners |  |  |  | https://www.youtube.com/watch?v=v6OuWDbw1n4
|  | General QandAs | Not started |  |  | TBD | Financial Aid |  |  | Campus Partners |  |  |  | https://www.youtube.com/watch?v=hqXx_Rrxgeo&t=1s
|  | The Fight Against Fraud | Not started |  |  | TBD | Financial Aid |  |  | Campus Partners |  |  |  | https://www.youtube.com/watch?v=wP-5OcRylqw&t=3s
|  | FAFSA® Update | Not started |  |  | TBD | Financial Aid |  |  | Campus Partners |  |  |  | https://fsapartners.ed.gov/training/federal-student-aid-fsa-training-conference/program/sessions/2023/fafsar-update
|  | 2024-2025 Federal Student Aid Handbook | Not started |  |  | TBD | Financial Aid |  |  | Campus Partners |  |  |  | https://fsapartners.ed.gov/knowledge-center/fsa-handbook/2024-2025
|  | FAFSA® Pell Eligibility and SAI Guide | Not started |  |  | TBD | Financial Aid |  |  | Campus Partners |  |  |  | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://fsapartners.ed.gov/sites/default/files/2024-01/20242025FAFSAPellEligibilityandSAIGuide.pdf
|  | Technical FAQ Known Issues Guide | Not started |  |  | TBD | Financial Aid |  |  | Campus Partners |  |  |  | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://fsapartners.ed.gov/sites/default/files/2024-03/TechnicalFAQandKnownIssues.pdf
|  | Foreign Earned Income Exclusion, SAI, and Maximum Pell Grant | Not started |  |  | TBD | Financial Aid |  |  | Campus Partners |  |  |  | https://fsatraining.ed.gov/mod/page/view.php?id=11840
|  | Reporting Foreign Earned Income Exclusion | Not started |  |  | TBD | Financial Aid |  |  | Campus Partners |  |  |  | https://fsatraining.ed.gov/mod/page/view.php?id=11839
|  | 60-Day Timeframe | Not started |  |  | TBD | Financial Aid |  |  | Campus Partners |  |  |  | https://fsatraining.ed.gov/mod/page/view.php?id=11838
|  | Enrollment Intensity | Not started |  |  | TBD | Financial Aid |  |  | Campus Partners |  |  |  | https://fsatraining.ed.gov/mod/page/view.php?id=11836
|  | Calculating Scheduled Pell Grant | Not started |  |  | TBD | Financial Aid |  |  | Campus Partners |  |  |  | https://fsatraining.ed.gov/mod/page/view.php?id=11835
|  | Crossover Payment Period & Pell Grant Awarding | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11834
|  | Family Size | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11833
|  | Child Support | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11837
|  | Divorced Parents | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11832
|  | Manual Tax Information | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11831
|  | Negative Student Aid Index | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11830
|  | Packaging Without Alternate SAI's | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11829
|  | Campus-Based Aid in COD | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11828
|  | Reporting Federal Work-Study | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11827
|  | Emergency Financial Assistance | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11826
|  | Professional Judgment, Dependency Status, and Verification Live Webinar June 15, 2023 | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11062
|  | Student Aid Index (SAI) – Part 1 Live Webinar June 22, 2023 | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11064
|  | Student Aid Index (SAI) – Part 2 Live Webinar June 27, 2023 | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11065
|  | Pell Minimums, Maximums, and In Between Live Webinar July 6, 2023 | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11066
|  | The FAA’s Role in FAFSA Simplification Live Webinar July 11, 2023 | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11067
|  | ISIR vs. ISIR Live Webinar June 13, 2023 | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/page/view.php?id=11061
|  | Cost of Attendance and Financial Need | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/lesson/view.php?id=10885&pageid=77581
|  | Federal Need Analysis | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/mod/lesson/view.php?id=10884
|  | https://fsatraining.ed.gov/course/view.php?id=409 | Not started |  |  | TBD | [7 empty] | https://fsatraining.ed.gov/course/view.php?id=409
|  | FAFSA SIMPLIFICATION IMPLEMENTATION SCHOOL CHECKLIST | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/FAFSA_Simplification_Implementation_Checklist.pdf
|  | FAFSA SIMPLIFICATION PELL GRANT ELIGIBILITY AND SAI PROCESS FLOW EFFECTIVE 2024-25 FAFSA | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/FAFSA_Methodology_Determination_Pell_Title_IV.pdf
|  | The FAFSA Simplification Act and Professional Judgment | Not started |  |  | TBD | [7 empty] | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/PJ_Changes_2-Pager.pdf
|  | FAFSA Simplification Communication Samples | Not started |  |  | TBD | [7 empty] | https://www.nasfaa.org/fafsa_simplification_communication_samples
|  | NASFAA Self-Study Guides | Not started |  |  | TBD | [7 empty] | https://www.nasfaa.org/Self_Study_Guides
|  | NASFAA Webinars | Not started |  |  | TBD | [7 empty] | https://www.nasfaa.org/Webinars_Live_and_On_Demand
|  | FAFSA Simplification Web Center | Not started |  |  | TBD | [7 empty] | https://www.nasfaa.org/fafsa_simplification
TBD
TBD
PIO/Marketing Communication Plan | Internal | Edit email templates for campus distribution | Not started |  |  | TBD
|  | Send email to camps stakeholders summarizing FAFSA Simplification. Inform Campus Offices of Impacts | Not started |  |  | TBD
|  | Send email to campus stakeholders regarding delays in Department of Ed. FAFSA simplification roll-out | Not started |  |  | TBD
|  | Send email message to campus stakeholders regarding office closures | Not started |  |  | TBD
|  | Send email to pertinent campus stakeholders regarding FTI impact | Not started |  |  | TBD
|  | Send email to campus stakeholders regarding emergency aid process | Not started |  |  | TBD
|  | Send email to campus stakeholders regarding delays in financial aid distribution | Not started |  |  | TBD
|  | Send email to campus stakeholders notifying them that ISIR's have arrived and processing can begin | Not started |  |  | TBD
|  | Send email to campus stakeholders giving an update on processing | Not started |  |  | TBD
|  | Send an email to campus stakeholders notifying them when aid will disburse | Not started |  |  | TBD
|  |  | Not started |  |  | TBD
|  | Create and distribute FAFSA Simplification talking points for campus partners | Not started |  |  | TBD
|  | Create and distribute office closure talking points for campus partners | Not started |  |  | TBD
|  | Create and distribute financial aid processing updates for campus partners | Not started |  |  | TBD
|  | Create and distribute financial aid distribution delays talking points for campus partners | Not started |  |  | TBD
|  | Create and distribute FAFSA completion talking points for campus partners | Not started |  |  | TBD
TBD
TBD
TBD
TBD
TBD
| Current and Prospective Student Complete FAFSA | Create and distribute Social Media Posts regarding FAFSA completion | Not started |  |  | TBD
|  | Create and send Email Messages to students regarding FAFSA completion | Not started |  |  | TBD
|  | Create Posters/Signage on-campus for FAFSA completion | Not started |  |  | TBD
|  | Create and send email message to students promoting the benefits of FAFSA simplification | Not started |  |  | TBD
|  | Create canvas announcement regarding FAFSA completion | Not started |  |  | TBD
TBD
TBD
TBD
| FAFSA Application Status Update | Create Social Media Posts regarding office closures | Not started |  |  | TBD
|  | Create Email Messages regarding office closures | Not started |  |  | TBD
|  | Utilize ctcLink 3C messaging | Not started |  |  | TBD
|  | No SAI Proration - communicate options of emergency funds and other resources | Not started |  |  | TBD
|  | Send email to FAFSA applicants regarding delays | Not started |  |  | TBD
|  | Send email to FAFSA applicants regarding financial aid status updates | Not started |  |  | TBD
|  | Send email to FAFSA applicants regarding financial aid distribution | Not started |  |  | TBD
|  | Send email to FAFSA applicants regarding emergency aid | Not started |  |  | TBD
|  | Send emails to students regarding relevant Dept. of Ed updates. | Not started |  |  | TBD
|  | Create Canvas announcement regarding financial aid awarding | Not started |  |  | TBD

## Key
RACI Key:
R: Responsible (responsible for completing the task)
A: Accountable (ultimately answerable for the task's completion or outcome)
C: Consulted (need to provide input or feedback before the task can be completed)
I: Informed (need to be kept in the loop about the task's progress)
Project Health
On Track: The project is on schedule, within scope, and within budget. Project resources are available for project activities when needed.
At Risk: There are risks and/or issues that might impact achievement of the project's objectives.
Off Track: There are significant issues that have impacted achievement of the project's objectives.
Status Key:
Not Started
Waiting
Prepping
Started
Nearing Completion
On Hold
Cancelled
Completed
Dependencies:
Dependencies refer to the relationships between tasks or activities within a project. A dependency exists when the completion or progress of one task is reliant on the completion of another task.
None
Department of Ed
State Board of Community and Technical Colleges
Washington Student Achievement Council
Internal
State Agency or College Responsible
TBD
College
SBCTC
WSAC
Other

## Key Links
Training Information
Completing the FAFSA
What is FAFSA? | https://www.youtube.com/watch?v=NmEP38x-1Z8
Preparing for the FAFSA Form
FSA Preparing for the FAFSA Form Youtube Playlist | https://www.youtube.com/playlist?list=PLtr3wy4M_CJ18cBXJb2r5mzyFoh9e9mcl
FSA Account Username & Password (FSA ID) Youtube Playlist | https://www.youtube.com/playlist?list=PLtr3wy4M_CJ1BWCzxHUf--IpLfh81J98n
How to Create an Account and Username (FSA ID) for StudnetAid.gov | https://www.youtube.com/watch?v=iTb7hMVtzco&list=PLtr3wy4M_CJ1BWCzxHUf--IpLfh81J98n
Troubleshooting Your Account Username and Password (FSA ID) | https://www.youtube.com/watch?v=lIwnEbOXSGg&list=PLtr3wy4M_CJ1BWCzxHUf--IpLfh81J98n&index=2
How Do I Create a StudentAid.gov Account if I Don't Have a Social Security Number | https://www.youtube.com/watch?v=Bu_EfT5_qtM
Applying for Finanical Aid
FSA Preparing for the FAFSA Form Youtube Playlist | https://www.youtube.com/playlist?list=PLtr3wy4M_CJ18cBXJb2r5mzyFoh9e9mcl
Applying for Finanical Aid With the FAFSA Form | https://www.youtube.com/watch?v=UupEQdS2VMY&list=PLtr3wy4M_CJ18cBXJb2r5mzyFoh9e9mcl
Who Is a Contributor on 24/25 FAFSA Form | https://www.youtube.com/watch?v=UOgIb7StyPU
Understand and Prepare FAFSA Form Contributors | https://www.youtube.com/watch?v=u8uubc08CDE&list=PLtr3wy4M_CJ18cBXJb2r5mzyFoh9e9mcl&index=2
Create an Access Your StudentAid.gov Account | https://www.youtube.com/watch?v=Pitb_aIQBVc&list=PLtr3wy4M_CJ18cBXJb2r5mzyFoh9e9mcl&index=3
Gather Information Required To Complete the FAFSA Form | https://www.youtube.com/watch?v=IpjwM6zzdPc&list=PLtr3wy4M_CJ18cBXJb2r5mzyFoh9e9mcl&index=4
Completing the FAFSA Form FSA Playlist
FSA Completing the FAFSA Form Youtube Playlist | https://www.youtube.com/playlist?list=PLtr3wy4M_CJ1dh4_EU1dkacmXyilGn-8m
Starting Your 2024-25 FAFSA Form | https://www.youtube.com/watch?v=Zkw463ke8ho&list=PLtr3wy4M_CJ1dh4_EU1dkacmXyilGn-8m
Comple the Personal Circumstances and Demographics Sections of the FAFSA From | https://www.youtube.com/watch?v=AaDQTgTUiXw&list=PLtr3wy4M_CJ1dh4_EU1dkacmXyilGn-8m&index=2
Complete the Financials Section of the 24-25 FAFSA Form | https://www.youtube.com/watch?v=f5HYetfElfM&list=PLtr3wy4M_CJ1dh4_EU1dkacmXyilGn-8m&index=3
Select Schools to Include on Your 24-25 FAFSA Form | https://www.youtube.com/watch?v=f5HYetfElfM&list=PLtr3wy4M_CJ1dh4_EU1dkacmXyilGn-8m&index=4
Review, Sign,and Submit Your 24-25 FAFSA Form | https://www.youtube.com/watch?v=HNrgGxASYRY&list=PLtr3wy4M_CJ1dh4_EU1dkacmXyilGn-8m&index=5
2024-2025 FAFSA FAQ's
Why Do My Contributors and I Need Our Own StudentAid.gov Accounts | https://www.youtube.com/watch?v=3c0jWxxyx6s&list=PLtr3wy4M_CJ2Hrd0UwCAWJOgOPu8l_ZLf&index=4
What Does It Mean To Provide Consent and Approval on the 2024–25 FAFSA® Form? | https://www.youtube.com/watch?v=zd21zLLR6yw&list=PLtr3wy4M_CJ2Hrd0UwCAWJOgOPu8l_ZLf&index=5
How Do I Complete the 2024–25 FAFSA® Form If My Parents Are Divorced or Separated? | https://www.youtube.com/watch?v=Ba2irkCtYvo&list=PLtr3wy4M_CJ2Hrd0UwCAWJOgOPu8l_ZLf&index=6
How Do I Complete the 2024–25 FAFSA® Form If My Parent Is a Noncitizen? | https://www.youtube.com/watch?v=NSy2_rYJVBk
FAFSA Overview | https://www.youtube.com/watch?v=emUDDQSFYRI&list=PL23B9A23CD8DD82DD&index=1
Next Steps After Submitting Your FAFSA Form
FSA Next Steps After Submitting Your FAFSA Form | https://www.youtube.com/playlist?list=PLtr3wy4M_CJ1QiU3gCEUDm9H8AZaPm4SP
What Happens After Submittigng Your FAFSA Form | https://www.youtube.com/watch?v=lXY5GBumXcc&list=PLtr3wy4M_CJ1QiU3gCEUDm9H8AZaPm4SP&index=1
What Happens After Your FAFSA Form is Processed | https://www.youtube.com/watch?v=fqCrS6ETCAs&list=PLtr3wy4M_CJ1QiU3gCEUDm9H8AZaPm4SP&index=2
Where's My Financial Aid | https://www.youtube.com/watch?v=I1EbAs2XpgE&list=PLtr3wy4M_CJ1QiU3gCEUDm9H8AZaPm4SP&index=3
What's Changed for the 24/25 FAFSA Form | https://www.youtube.com/watch?v=UOgIb7StyPU
Outreach Partners
2024-25 FAFSA Form Preview Presentation | https://fsapartners.ed.gov/knowledge-center/library/application-processing/2023-07-31/2024-25-fafsa-form-preview-presentation
FAFSA Changes FAQ Webpage | https://financialaidtoolkit.ed.gov/tk/announcement-detail.jsp?id=fafsa-changes-faqs
Understanding the new FAFSA Submission Summary | https://www.youtube.com/watch?v=jHaAtCMmB2c
How to Compare Financial Aid Offers and Schools | https://www.youtube.com/watch?v=puPi3DPNMDw
Why Should I Complete the 24/25 FAFSA Form | https://www.youtube.com/watch?v=U2FkQ_KxQRI
Special Student Populations and Circumstances for 2024-25 FAFSA Form Webinar | https://www.youtube.com/watch?v=zpGjs4yg1z8&t=2078s
May 2023 ¦ FAFSA Changes: An Overview | https://www.youtube.com/watch?v=kSHQmtSQFvo&list=PLyCvB-1-qvl8RaytPnfFbpbXRrhXpkmwh&index=3
August 2023 ¦ College Access Professionals 2024-25 FAFSA Demonstration | https://www.youtube.com/watch?v=k26QnHn7Xcs&list=PLyCvB-1-qvl8RaytPnfFbpbXRrhXpkmwh&index=4
FAFSA Overview Fact Sheet | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://financialaidtoolkit.ed.gov/resources/fafsa-changes-overview.pdf
October 2023 ¦ Financial Aid Bootcamp: How to Prepare for the 2024-25 FAFSA Form | https://www.youtube.com/watch?v=Fao1ZwhN_no
October 2023 ¦ Financial Aid Bootcamp: Dependent Student 2024-25 Prototype Preview | https://www.youtube.com/watch?v=EqpZ45wIzkc
October 2023 ¦ Financial Aid Bootcamp: Independent Student 2024-25 Prototype Preview | https://www.youtube.com/watch?v=GBhikcNFYvM
December 2023 ¦ 2024-25 FAFSA Contributor Prep | https://www.youtube.com/watch?v=JZUBlw1b7_I
February 2024 ¦ Parent Guide to Federal Financial Aid | https://www.youtube.com/watch?v=2fdXF6IXpbw
Adult Student FAQ | https://financialaidtoolkit.ed.gov/tk/outreach/target/adults.jsp
Parent FAQ | https://financialaidtoolkit.ed.gov/tk/outreach/target/parents.jsp
Counselors and Mentors Handbook on Federal Student Aid | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://financialaidtoolkit.ed.gov/resources/2024-25-counselors-handbook.pdf
Federal Student Aid Handbook Glossary | https://fsapartners.ed.gov/knowledge-center/fsa-handbook/glossary
Make a Financial Aid Presentation | https://financialaidtoolkit.ed.gov/tk/outreach/presentation.jsp
FAFSA Submission Summary Sample (English) | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://financialaidtoolkit.ed.gov/resources/2024-25-fafsa-submission-summary-sample.pdf
FAFSA Submission Summary Sample (Spanish) | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://financialaidtoolkit.ed.gov/resources/2024-25-fafsa-submission-summary-sample-spanish.pdf
FAFSA PDF (English) | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://studentaid.gov/sites/default/files/2024-25-fafsa.pdf
FAFSA PDF (Spanish) | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://studentaid.gov/sites/default/files/2024-25-fafsa.pdf
2024-25 FAFSA Frequently Asked Questions | https://fsapartners.ed.gov/knowledge-center/topics/fafsa-simplification-information/2024-25-fafsa-frequently-asked-questions
How To Submit the 2024–25 FAFSA® Form if Your Contributor Doesn’t Have an SSN | https://studentaid.gov/announcements-events/fafsa-support/contributor-social-security-number
What should I do if I have an unusual circumstance and can’t provide parent information? | https://studentaid.gov/help/unusual-circumstances
2024–25 FAFSA® Help | https://studentaid.gov/apply-for-aid/fafsa/filling-out/help
Filling Out the FAFSA® Form | https://studentaid.gov/apply-for-aid/fafsa/filling-out
7 Key Changes Coming to the 2024–25 FAFSA® Experience | https://studentaid.gov/articles/fafsa-changes-coming/
10 Common FAFSA Mistakes To Avoid | https://studentaid.gov/articles/10-fafsa-mistakes-to-avoid/
9 Myths About the FSA ID | https://studentaid.gov/articles/9-myths-fsa-id/
8 Easy Steps for Parents Completing the 2023–24 FAFSA® Form | https://studentaid.gov/articles/fafsa-for-parents/
Explainer: How to Get an FSA ID without a Social Security Number | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/FSA_ID_without_SSN.pdf
Spanish Explainer: How to Get an FSA ID without a Social Security Numbe | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/Spanish_FSA_ID_without_SSN.pdf
FAFSA Simplification Brief for Campus Partners | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/FAFSA_Simplification_Brief_Campus_Partners.pdf
Tip Sheet for Adult Learners | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/2023-24_Tip_Sheet_Adult_Learners.pdf
Tip Sheet for Financial Aid Administrators Working with Refugee and Asylee Students | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/Tip_Sheet_FAA_Refugee_Asylee_Students.pdf
Tip Sheet for Servicemembers and Veterans | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/2023-24_Tip_Sheet_Servicemen_Veterans.pdf
Eligibility for Students With Criminal Convictions | https://studentaid.gov/understand-aid/eligibility/requirements/criminal-convictions
Tip Sheet for Unaccompanied Homeless Youth (UHY) | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/Tip_Sheet_for_Unaccompanied_Homeless_Youth.pdf
Tip Sheet for Undocumented Students | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/2023-24_Tip_Sheet_Undocumented_Students.pdf
Data Sharing Decision Tree | https://askregs.nasfaa.org/resources/GetResourceFile/21
Data Use and Considerations Under the FUTURE Act and FAFSA® Simplification Act | https://fsapartners.ed.gov/sites/default/files/attachments/2024-01/2023FSAConfSessionBO10DataUseConsiderationUnderFutureFAFSA_Final.pdf
Financial Aid Staff (FSA Training May Require Account)
Data Use and Considerations Under the FUTURE Act and FAFSA® Simplification Act | https://www.youtube.com/watch?v=XTaHoIBW2k0&t=41s
FAFSA Simplification Application and Need Analysis | https://www.youtube.com/watch?v=JY7YBLZ8qeA&t=2s
Calculating a Federal Pell Grant | https://www.youtube.com/watch?v=v6OuWDbw1n4
General QandAs | https://www.youtube.com/watch?v=hqXx_Rrxgeo&t=1s
The Fight Against Fraud | https://www.youtube.com/watch?v=wP-5OcRylqw&t=3s
FAFSA® Update | https://fsapartners.ed.gov/training/federal-student-aid-fsa-training-conference/program/sessions/2023/fafsar-update
2024-2025 Federal Student Aid Handbook | https://fsapartners.ed.gov/knowledge-center/fsa-handbook/2024-2025
FAFSA® Pell Eligibility and SAI Guide | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://fsapartners.ed.gov/sites/default/files/2024-01/20242025FAFSAPellEligibilityandSAIGuide.pdf
Technical FAQ Known Issues Guide | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://fsapartners.ed.gov/sites/default/files/2024-03/TechnicalFAQandKnownIssues.pdf
Foreign Earned Income Exclusion, SAI, and Maximum Pell Grant | https://fsatraining.ed.gov/mod/page/view.php?id=11840
Reporting Foreign Earned Income Exclusion | https://fsatraining.ed.gov/mod/page/view.php?id=11839
60-Day Timeframe | https://fsatraining.ed.gov/mod/page/view.php?id=11838
Enrollment Intensity | https://fsatraining.ed.gov/mod/page/view.php?id=11836
Calculating Scheduled Pell Grant | https://fsatraining.ed.gov/mod/page/view.php?id=11835
Crossover Payment Period & Pell Grant Awarding | https://fsatraining.ed.gov/mod/page/view.php?id=11834
Family Size | https://fsatraining.ed.gov/mod/page/view.php?id=11833
Child Support | https://fsatraining.ed.gov/mod/page/view.php?id=11837
Divorced Parents | https://fsatraining.ed.gov/mod/page/view.php?id=11832
Manual Tax Information | https://fsatraining.ed.gov/mod/page/view.php?id=11831
Negative Student Aid Index | https://fsatraining.ed.gov/mod/page/view.php?id=11830
Packaging Without Alternate SAI's | https://fsatraining.ed.gov/mod/page/view.php?id=11829
Campus-Based Aid in COD | https://fsatraining.ed.gov/mod/page/view.php?id=11828
Reporting Federal Work-Study | https://fsatraining.ed.gov/mod/page/view.php?id=11827
Emergency Financial Assistance | https://fsatraining.ed.gov/mod/page/view.php?id=11826
Professional Judgment, Dependency Status, and Verification Live Webinar June 15, 2023 | https://fsatraining.ed.gov/mod/page/view.php?id=11062
Student Aid Index (SAI) – Part 1 Live Webinar June 22, 2023 | https://fsatraining.ed.gov/mod/page/view.php?id=11064
Student Aid Index (SAI) – Part 2 Live Webinar June 27, 2023 | https://fsatraining.ed.gov/mod/page/view.php?id=11065
Pell Minimums, Maximums, and In Between Live Webinar July 6, 2023 | https://fsatraining.ed.gov/mod/page/view.php?id=11066
The FAA’s Role in FAFSA Simplification Live Webinar July 11, 2023 | https://fsatraining.ed.gov/mod/page/view.php?id=11067
ISIR vs. ISIR Live Webinar June 13, 2023 | https://fsatraining.ed.gov/mod/page/view.php?id=11061
Cost of Attendance and Financial Need | https://fsatraining.ed.gov/mod/lesson/view.php?id=10885&pageid=77581
Federal Need Analysis | https://fsatraining.ed.gov/mod/lesson/view.php?id=10884
https://fsatraining.ed.gov/course/view.php?id=409 | https://fsatraining.ed.gov/course/view.php?id=409
NASFAA (May require an account)
FAFSA SIMPLIFICATION IMPLEMENTATION SCHOOL CHECKLIST | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/FAFSA_Simplification_Implementation_Checklist.pdf
FAFSA SIMPLIFICATION PELL GRANT ELIGIBILITY AND SAI PROCESS FLOW EFFECTIVE 2024-25 FAFSA | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/FAFSA_Methodology_Determination_Pell_Title_IV.pdf
The FAFSA Simplification Act and Professional Judgment | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.nasfaa.org/uploads/documents/PJ_Changes_2-Pager.pdf
FAFSA Simplification Communication Samples | https://www.nasfaa.org/fafsa_simplification_communication_samples
NASFAA Self-Study Guides | https://www.nasfaa.org/Self_Study_Guides
NASFAA Webinars | https://www.nasfaa.org/Webinars_Live_and_On_Demand
FAFSA Simplification Web Center | https://www.nasfaa.org/fafsa_simplification