## MPSR Dec2024
SBCTC Major Project Status Reports - For Projects in Design or Construction in 2023-25
Estimates as of December 2024
Project | Approp. | OFM | SBCTC | MPSR | Current BI |  | Gross | MACC |  |  | Construction/
College/Description | Code | Proj No | Proj No | Received | Ch-Ses-Sec | Bid Date | Square Footage | Pre-design | Current Budget | Actual to date | Completion Date
Bates: Fire Service Training Center | A10/D02 | 40000130 |  |  |  | 2024-08-30 | 43094 | 22782833 | 29596827 | 0 | 2026-12-31
Bellevue College: Center for Transdisciplinary | A11, C14 | 40000168 |  |  |  | 2025-01-14 | 52000 | 30506965 | 38607543 | 0 | 2026-09-01
Bellingham Technical College: Campus Center Emergency | D25 | 40000916 |  |  |  | 2024-06-01 | 68093 | 11945366 | 11945366 | 1703328 | 2026-06-01
Cascadia College: CC5 Gateway building | C17 | 40000222 |  |  |  | - | 37203 | 24325425 | 24325425 | 0 | 2025-03-01
Centralia College: Teacher Ed & Family Development | C11 | 40000109 |  |  |  | 2025-06-01 | 18430 | 8946425 | 8946425 | 0 | 2027-06-30
Clark College: North County Satellite | U95, C01 | 30000135 |  |  |  | 2023-04-04 | 50000 | 44657741 | 41711000 | 45227700 | 2024-12-31
Edmonds Community College: Triton Learning Commons | C13 | 40000114 |  |  |  | - | 49820 | 23287124 | 23287124 | 0 | 2025-02-01
Everett Community College Baker Hall Replacement | A21/D03 | 40000190 |  |  |  | - | 50000 | 22336946 | 26625336 | 0 | 2024-12-01
Everett Community College Learning Resource Center | U90, C02 | 30000136 |  |  |  | 2021-07-01 | 70000 | 31056149 | 33776863 | 38953620 | 2023-01-01
Grays Harbor: Student Services | U88, C00 | 30000127 |  |  |  | 2021-12-14 | 69985 | 34870828 | 40130047 | 39420197 | 2024-03-05
Lake Washington: Center for Design | A07/D00 | 40000102 |  |  |  | 2024-01-23 | 56500 | 23288721 | 29732930 | 7228121 | 2026-01-27
Lower Columbia College: Center for Vocational & Transitional Studies | C09 | 40000106 |  |  |  | - | 54799 | 27442642 | 27442642 | 0 | 2025-08-01
North Seattle College: Library Building Renovation | U93, C04 | 30001451 |  |  |  | 2021-08-17 | 54359 | 21343488 | 23317000 | 23237000 | 2025-02-28
Olympic College: Innovation & Tech Learning | A08 | 40000103 |  |  |  | 2026-05-01 | 31864 | 23516648 | 23516648 | 0 | 2028-04-01
Olympic College: Shop Building Renovation | U97, A01 | 30000986 |  |  |  | 2022-05-17 | 16960 | 7011671 | 9883000 | 9883000 | 2024-09-20
Pierce FS College: Cascade Building Phase 3 | U98, A02 | 30000987 |  |  |  | 2020-08-25 | 59972 | 21106386 | 20061000 | 20102807 | 2023-08-21
Pierce FS College: Olympic South Asbestos Abatement | C28 | 40000516 |  |  |  | 2022-04-30 | 38800 |  | 18513474 | 17123946 | 2025-03-01
Pierce PY College: STEM building | A17, C18 | 40000293 |  |  |  | 2022-07-13 | 66500 | 25774620 | 34696228 | 35917499 | 2025-03-15
Renton Technical College: Health Sciences Center | C15 | 40000204 |  |  |  | - | 69992 | 32951531 | 32951531 | 0 | 2027-06-01
Shoreline College: Allied Health, Science, and Manufacturing | U81, C03 | 30000990 |  |  |  | 2021-04-09 | 51600 | 29221137 | 30350301 | 34792690 | 2023-10-06
Shoreline College: STE(A)M Education Center | C16/D05 | 40000214 |  |  |  | 2024-02-27 | 40500 | 22549273 | 27440508 | 5396394 | 2026-03-21
Skagit Valley College: Library/Culinary Arts | C12 | 40000110 |  |  |  | - | 39366 | 24019484 | 29549161 | 0 | 2027-03-01
South Seattle: Automotive Technology Renovation | U99, A03 | 30000988 |  |  |  | 2019-12-17 | 45590 | 16068902 | 18069673 | 19391196 | 2025-08-31
Spokane Community College: Apprenticeship Center | C10 | 40000107 |  |  |  | 2027-07-01 | 59683 | 25921016 | 25921016 | 0 | 2029-06-30
Spokane Falls Community College: Fine and Applied Arts building | U40, A20, C06 | 30001458 |  |  |  | 2020-06-30 | 59837 | 24850230 | 28322093 | 26402956 | 2024-10-05
Tacoma Community College: Center for Innovative Learning | C08/D01 | 40000104 |  |  |  | 2023-10-05 | 51325 | 21250948 | 27461300 | 29692474 | 2025-08-15
Wenatchee Valley College: Center for Technical Education | C07/D04 | 40000198 |  |  |  | - | 69980 | 34935223 | 39025512 | 0 | 2025-05-01
Wenatchee Valley College: Wells Hall Replacement | U05, A00 | 30000985 |  |  |  | 2019-10-02 | 69985 | 25029330 | 25107919 | 26837611 | 2025-03-31
* If MACC not provided in Major Project Status Reports, C-100 info used
SBCTC Major Project Status Reports - Projects that have been finalized
Project | Approp. | OFM |  | MPSR | Current Biennium |  | Gross |  |  |  | Construction/
College/Description | Code | Proj No |  | Received | Chp-Ses-Sec | Bid Date | Square Footage |  |  | MACC* | Completion Date
Bates Technical College - LRC/Vocational Building | H01 | 022684 |  | 2007-06-01 | 520-07-5150 | 2005-08-16 | 45000 |  |  | 9796387 | 2007-01-01
Bates Medical Mile Health Science Center | U80, A04 | 30000989 |  |  |  | 2018-07-26 | 68000 |  |  | 32893674 | 2021-10-01
Bates Technical College: Mohler Communication & Technology | I51/J16/S02 | 20082703 | S02-L324 | 2017-01-27 | 3-15-5111 | 2014-02-26 | 53591 |  |  | 19128242 | 2016-03-09
Bellevue Community College: "D" Building | G30,G31 | 041308 |  | 2007-06-28 | 488-05-765 | 2005-05-10 | 82617 |  |  | 9028500 | 2007-01-01
Bellevue College: Health Sciences Building | I50/J40/S01 | 20082702 | S01-L318 |  | 3-15-5110 | 2013-06-26 | 69914 |  |  | 23395817 | 2015-07-31
Bellevue Community College: Science and Technology | H71,I02 | 042690 |  | 2009-06-29 | 520-07-5155 | 2007-06-07 | 64238 |  |  | 27400609 | 2008-12-23
Bellingham Technical College - Welding/Auto Collision | G27,G72 | 041213 |  | 2007-07-02 | 488-05-767 | 2005-06-01 | 47455 |  |  | 12819681 | 2007-03-01
Bellingham Technical College - Instr Res Ctr (Rpl Bld. D,E, & F) | I27 | 20081223 |  | 2013-12-16 | 520-07-5237 | 2010-05-01 | 72885 |  |  | 17268350 | 2012-10-01
Big Bend Community College: Fine Arts Addition & GTA Bus Stop | H25 | 061309/082130 |  | 2009-01-05 | 520-07-5192 | 2007-07-01 | 11000 |  |  | 2493000 | 2008-06-01
Big Bend Community College: Professional-Technical Ed | T71/U84 | 30000981 | T71-M342 | 2017-01-27 | 3-15-5131 | 2018-04-11 | 76140 |  |  | 37078060 | 2020-10-23
Cascadia Community College - Center for the Arts | H74,I05 | 20042693 |  | 2010-06-14 | 520-07-5157 | 2008-04-30 | 53400 |  |  | 19797500 | 2009-10-02
Cascadia College: Center for Science and Technology (Moved to UW) | U79 | 30001453 |  |  |  |  | 66101 |  |  | 0 | 2022-01-01
Cascadia Community College - South Access | G70 | 022999 |  | 2008-12-31 | 520-07-5151 | 2007-12-12 | N/A |  |  | 7313000 | 2010-06-01
Centralia Community College: Science Replacement | H62,I55 | 042850 |  | 2009-06-30 | 520-07-5158 | 2007-04-15 | 69995 |  |  | 22787092 | 2009-03-06
Centralia College: Student Services | S12/T59 | 30000123 | T59-M338 | 2017-01-27 | 3-15-5118 | 2015-03-31 | 69900 |  |  | 25183412 | 2017-04-21
Clark College - Clark Center at WSU | F15,G11 | 002680 |  | 2006-01-03 | 488-05-738 | 2004-06-01 | 63334 |  |  | 12366000 | 2005-10-01
Clark College: Central Gaiser Hall Renovation | H18 | 061302 |  | 2008-06-30 | 520-07-5193 | 2006-07-01 | 27345 |  |  | 7832070 | 2008-03-01
Clark College: East County Satellite Campus | H70,I01 | 041689 |  | 2009-06-30 | 520-07-5159 | 2007-11-01 | 68542 |  |  | 20470000 | 2009-04-01
Clark College: Health & Advanced Technology (STEM) | I53/J17/S03 | 20082705 | S03-L328 |  | 3-15-5113 | 2014-06-17 | 69998 |  |  | 27542511 | 2016-06-23
Clark College: Penguin Student Union | COP | 043901 |  | 2006-01-03 | 26-03X-907(4)(c) | 2003-12-01 | 32883 |  |  | 6578000 | 2005-02-01
Clover Park Technical College: Allied Health/Health Sciences | H53/I12/K01 | 20062699 | K01-K257 | 2017-01-27 | 3-15-5104 | 2011-11-15 | 56468 |  |  | 14320663 | 2014-10-21
Clover Park Technical College: Center for Advanced Mfg | T38/COP | 30000984 | T38-M346 | 2017-01-27 | 3-15-5140 | 2018-03-01 | 62478 |  |  | 31945497 | 2020-01-25
Clover Park Technical College: Renovate Building 8 | H26 | 061310 |  | 2008-06-26 | 520-07-5196 | 2006-11-01 | 30083 |  |  | 5136000 | 2007-12-01
Clover Park Technical College: Student Center | COP/Local | 063022 |  | 2007-12-18 | 488-05-909(5)(c) | 2006-04-19 | 48037 |  |  | 13260000 | 2007-06-01 | includes bookstore
Columbia Basin College: Health Science Center | G37,G77,H61/Local | 041307 |  |  | 488-05-805 | 2005-06-05 | 66935 |  |  | 8400000 | 2006-09-08
Columbia Basin College: Rnv. Business Education "B" Building | I32 | 081315 |  | 2009-06-01 | 520-07-5241 | 2008-05-21 | 22500 |  |  | 4564500 | 2009-05-15
Columbia Basin College - Social Science Center | I52/S11/T78 | 20082704 | T78-M339 | 2017-01-27 | 3-15-5112 | 2015-07-01 | 66724 |  |  | 14797184 | 2016-12-21
Columbia Basin College: Vocational Building | I21 | 20081217 |  |  | 520-07-5243 | 2009-05-20 | 72241 |  |  | 16589000 | 2010-11-28
Columbia Basin College: WISE & T Bldg | H46,Local | 062409 |  | 2005-12-01 | 488-05-773/816 | 2004-06-01 | 21000 |  |  | 2854000 | 2005-09-01
Edmonds Community College: Mountlake Terrace Hall | G38 | 041311 |  | 2006-06-14 | 488-05-774 | 2004-09-01 | 57600 |  |  | 5833300 | 2005-12-01
Edmonds Community College - Mukilteo Hall & Black Box Theater | H02 | 022685/063019 |  | 2007-12-19 | 520-07-5152 | 2006-05-01 | 62735 |  |  | 11858885 | 2007-12-01
Edmonds Community College: Renovate Brier Hall & Bookstore | H23 | 061307/073030 |  | 2008-12-23 | 520-07-5197 | 2007-02-01 | 62614 |  |  | 9097095 | 2009-01-01 | includes bookstore
Edmonds Community College: Renovate Meadowdale Hall | I35 | 20081318 |  | 2010-06-10 | 520-07-5245 | 2008-10-01 | 36393 |  |  | 5534000 | 2010-03-01
Edmonds Community College: Science, Engin., & Tech Bldg (SET) | S15/U82 | 30000137 | S15-L330 | 2017-01-27 | 3-15-5123 | 2018-06-28 | 69910 |  |  | 37042016 | 2020-08-12
Everett Community College: Index Hall Replacement | I25,J07,K02 | 20081221 |  |  |  | 2011-07-26 | 69350 |  |  | 21019000 | 2015-03-23
Everett Community College: Science and Art | G40,H04,H45 | 041305 |  | 2007-06-29 | 488-05-775 & 776 | 2004-05-01 | 85630 |  |  | 18435674 | 2006-10-01
Everett Community College: Undergraduate Education Center | H73,I04 | 042692 |  | 2009-06-30 | 520-07-5163 | 2007-05-01 | 100000 |  |  | 32171000 | 2008-12-12
Grays Harbor College: Replacement Instruct Bldg | G43,G73 | 041204 |  | 2007-06-30 | 488-05-779 | 2005-02-01 | 71755 |  |  | 15533000 | 2007-07-01
Grays Harbor College: Science Replacement (SMArt) | I30/J10/S25 | 20081226 | S25-L319 | 2017-01-27 | 3-15-5108 | 2013-07-02 | 70325 |  |  | 31985608 | 2015-07-01
Grays Harbor College: Vocational Education | H19 | 061303 |  | 2007-12-18 | 520-07-5200 | 2006-12-07 | 45050 |  |  | 3908000 | 2007-11-26
Green River Community College - Computer Technology Center | G45 | 042682 |  | 2005-06-01 | 488-05-780 | 2003-07-01 | 31250 |  |  | 7358200 | 2005-06-01
Green River Community College - Humanities & Clsrm. Bldg. | I08 | 20061205 |  |  | 520-07-5201 | 2009-05-28 | 80039 |  |  | 23004000 | 2011-03-05
Green River Community College - Science | G17,H68 | 012688 |  |  | 488-05-744 | 2005-06-01 | 76000 |  |  | 20689000 | 2006-12-31
Green River Community College: Science, Math & Technology | J31/K04 | 30000130 | K04-K259 |  | None | 2011-06-08 | 60900 |  |  | 14093353 | 2016-06-01
Green River Community College: Trades & Industry Complex | I26/J08/S00 | 20081222 | S00-L322 | 2017-01-27 | 3-15-5107 | 2014-02-06 | 76684 |  |  | 22094384 | 2017-03-31
Highline College: Health and Life Sciences | T82/U85 | 30000983 | T82-M345 | 2017-01-27 | 3-15-5133 | 2018-03-22 | 46746 |  |  | 20060592 | 2020-01-06
Highline: Student Union | COP | 023905 |  | 2005-12-23 | SSB6155.907(c) | 2003-04-01 | 45306 |  |  | 9283000 | 2005-01-01
Lake Washington: Allied Health Building | H51,I58,J00 | 062697 |  | 2011-12-31 | 520-07-5207 | 2009-07-01 | 83500 |  |  | 19405000 | 2011-12-01
Lower Columbia College - Fine Arts Center | G28,H07 | 041214 |  | 2008-06-30 | 520-07-5170 | 2006-07-19 | 54000 |  |  | 12148400 | 2008-03-21
North Seattle College: Allied Health & Technology | J30/K19 | 30000129 | K19-K357 | 2017-01-27 | 3-15-5121 | 2012-07-01 | 69203 |  |  | 18497225 | 2020-12-01
North Seattle Community College: Employment Resource Cntr | I13,J01 | 20062851 |  | 2012-06-15 | 497-09-5168 | 2009-07-28 | 45052 |  |  | 17804000 | 2011-03-01
Olympic College: College Instruction Center | K18/T52 | 30000122 | T52-M337 |  | 3-15-5117 | 2013-06-01 | 75322 |  |  | 37553888 | 2018-07-15
Olympic College - Humanities Building/Parking Lot | H16, I07 | 20061204 |  | 2013-06-21 | 520-07-5213 | 2008-03-01 | 169000 |  |  | 22437044 | 2013-01-01
Olympic College - Science and Technology | G42,G49 | 041202/951 |  | 2007-12-21 | 520-07-5164/5172 | 2005-12-01 | 57598 |  |  | 15041000 | 2007-03-30 | *childcare center
Olympic College: Sophia Bremer Childcare Development Cntr | J25 | 30000115 |  |  | 497-09-5215 | 2009-11-01 | 16523 |  |  | 2888000 | 2010-09-01
Peninsula College: Allied Health & Early Childhood Dev. Center | S13/T93 | 30000126 | T93-M340 | 2017-01-27 | 3-15-5119 | 2015-06-01 | 42311 |  |  | 16982736 | 2017-03-31
Peninsula College: Business and Humanities Center (Maier Hall) | I22 | 20081218 |  |  | 520-07-5257 | 2009-11-24 | 62950 |  |  | 26000000 | 2011-03-21
Peninsula College - Library Renovation | H21 | 061305 |  | 2008-12-23 | 520-07-5215 | 2006-12-01 | 35430 |  |  | 8645000 | 2008-04-01
Peninsula College - Replacement Science & Tech | H05 | 041208 |  | 2007-07-02 | 488-05-787 | 2005-08-01 | 57500 |  |  | 16348000 | 2007-02-01
Pierce College Fort Steilacoom: Cascade Core Renov Phase I | H31,I10 | 061326 |  | 2009-06-24 | 520-07-5217 | 2007-08-21 | 57968 |  |  | 10300000 | 2009-04-17
Pierce College Fort Steilacoom: Cascade Core Renov Phase 2 |  | 20081321 |  | 2015-06-22 |  | 2009-07-01 | 75282 |  |  | 17185209 | 2015-05-06
Pierce College Fort Steilacoom: Health Education Renov. | G42 | 041951 |  | 2007-12-21 | 488-05-778 | 2006-02-01 | 45539 |  |  | 4197600 | 2007-09-24
Pierce College Fort Steilacoom: Science and Technology | H75, I06 | 20042694 |  | 2013-12-16 | 520-07-5174 | 2012-01-10 | 80645 |  |  | 23203000 | 2012-12-31
Pierce College Puyallup: Communication & Allied Health | H72,I03 | 20042691 |  |  | 520-07-5176 | 2008-05-01 | 61597 |  |  | 17875000 | 2010-07-15 | *childcare center
Pierce College Puyallup - Phase III Childcare/Second Entry | G14 | 002676 |  | 2007-06-29 | 488-05-740 | 2006-03-01 | 7735 |  |  | 2093980 | 2007-03-01
Pierce College Puyallup: Student Fitness Center | COP | 053015 |  | 2008-06-30 | 488-05-909(5)(m) | 2007-02-21 | 16636 |  |  | 4123900 | 2008-05-08
Renton Technical College: Automotive Complex Renovation | S14/T64 | 30000134 | T64-M343 | 2017-01-27 | 3-15-5122 | 2015-05-28 | 63550 |  |  | 14497111 | 2017-03-02
Renton Technical College - Portable Replacement | G57,H08 | 041215 |  | 2007-07-19 | 488-05-791 | 2006-05-01 | 11088 |  |  | 2067200 | 2007-07-01
Seattle Central College: Maritime Academy | J28/S04 | 30000120 | S04-L320 | 2017-01-27 | 3-15-5115 | 2014-11-01 | 26514 |  |  | 13047917 | 2016-08-26
Seattle Central Community College: Renovate Edison North | I31 | 20081314 |  | 2011-12-31 | 520-07-5261 | 2008-12-01 | 63860 |  |  | 12507000 | 2010-04-01
Seattle Central Community College: Rnv Visual Communications | H20 | 061304 |  | 2008-12-31 | 520-07-5221 | 2007-01-01 | 35000 |  |  | 5585746 | 2007-12-01
Seattle Central Replace Science & Math | G42,G59,F27 | 021215 |  | 2006-12-31 | 488-05-754/778/793 | 2004-12-01 | 67440 |  |  | 14393506 | 2006-06-01
Seattle Central Broadway Edison Renovation | G42 | 041310 |  | 2007-06-20 | 488-05-778 | 2005-06-01 | 32000 |  |  | 4367101 | 2006-06-01
Seattle Central College: Wood Construction Center | I20/J02 | 20081216 | J02-AF9G | 2016-06-01 |  | 2010-02-04 | 60857 |  |  | 15982983 | 2014-01-31
South Seattle College: Integrated Ed. Cntr. | S17/T99 | 30000128 | T99-M341 | 2016-06-30 | 3-15-5120 | 2015-12-16 | 57550 |  |  | 19325021 | 2018-07-31
Seattle South Community College - Repl Duwamish Building | H11 | 051854 |  | 2008-12-10 | 520-07-5189 | 2006-05-25 | 34250 |  |  | 8941693 | 2008-07-01
Shoreline Community College: Automotive Bldg | H57,I42 | 20082413 |  |  | 520-07-5223/5263 | 2009-02-01 | 21915 |  |  | 4353000 | 2009-11-01
Shoreline Community College PUB | COP | 063021 |  | 2008-07-16 | 488-05-909(5)(h) | 2006-05-01 | 52000 |  |  | 9808000 | 2007-12-01
Skagit Valley College: Academics and Student Support | I28/J09/COP | 20081224 | 147-K436 |  |  | 2012-06-06 | 72858 |  |  | 21425615 | 2015-05-01
Skagit Valley College - Science Building Replacement | H06,I00 | 20041209 |  | 2010-06-07 | 520-07-5180 | 2007-10-16 | 69000 |  |  | 21157000 | 2009-08-11
Spokane Community College: Renovate Building 7 | I36 | 20081319 |  |  | 520-07-5266 | 2009-06-24 | 35661 |  |  | 6882000 | 2010-11-10
Spokane Community College: South Wing Renovation | T49/U83 | 30000982 | T49-M344 | 2017-01-27 | 3-15-5132 | 2016-12-15 | 50849 |  |  | 17664198 | 2023-03-29
Spokane Community College: Replace Technical Ed Bldg | I24 | 20081220 |  | 2015-05-18 | 520-07-5267 | 2009-08-05 | 73275 |  |  | 10090300 | 2012-02-29
Spokane Community College: Science Building | G26 | 041212 |  |  | 488-05-799 | 2005-02-01 | 65288 |  |  | 10088000 | 2006-03-01
Spokane Falls: Business and Social Science Replacement | H10 | 051853 |  | 2008-06-24 | 520-07-5190 | 2006-03-08 | 70533 |  |  | 13106000 | 2007-12-15
Spokane Falls: General Classroom and Early Learning Bldg (Pt1) | I57 | 20062696 |  | 2014-12-01 | 520-07-5229 | 2012-04-18 | 47497 |  |  | 9947000 | 2014-09-15
Spokane Falls: General Classroom and Early Learning Bldg (Pt2) | I57 | 20062696 |  | 2015-05-18 | 520-07-5229 | 2013-05-01 | 15242 |  |  | 3499000 | 2015-08-19
Spokane Falls: Renovate Music Building 15 | I37 | 20081320 |  |  | 520-07-5270 | 2009-06-10 | 47571 |  |  | 10307000 | 2011-06-14
SPSCC: Building 22 Renovation | I33 | 20081316 |  |  | 520-07-5265 | 2009-07-15 | 76470 |  |  | 13265000 | 2010-07-25
SPSCC General Education Complex | G15 | 002679 |  | 2005-12-23 | 488-05-741 | 2003-12-01 | 61800 |  |  | 13624248 | 2005-09-01
South Puget Sound Community College: Learn. Resource Ctr. | H52/I59/K00 | 20062698 | K00-K256 | 2016-06-30 |  | 2011-10-06 | 89308 |  |  | 23418628 | 2014-11-12
SPSCC Science Complex | H60,I56 | 042695 |  | 2008-12-31 | 520-07-5181 | 2007-07-21 | 55300 |  |  | 21186226 | 2009-02-01
Tacoma Community College: Harned Center for Health Careers | I49/J15/K20 | 20082701 | K20-K358 |  | 3-15-5109 | 2012-08-28 | 69715 |  |  | 21888722 | 2015-10-01
Tacoma Community College - Replace Science Building | G18H00 | 012687 |  | 2007-07-05 | 488-05-745 | 2005-07-01 | 73000 |  |  | 19687000 | 2007-02-19
Tacoma: Information Technology Building | G23 | 022683 |  | 2005-12-23 | 488-05-760 | 2003-07-01 | 54300 |  |  | 11449000 | 2005-02-01
Tacoma Community College: Renovation Bldg 7 | G64 | 041313 |  | 2007-12-20 | 520-07-5185 | 2006-06-15 | 20000 |  |  | 3009000 | 2007-07-13
Walla Walla Community College - Basic Skills/Computer Lab | H03 | 022686 |  | 2008-01-24 | 520-07-5154 | 2006-06-28 | 37150 |  |  | 4144000 | 2007-07-01
Walla Walla Community College - Health Sciences | G66 | 041211 |  | 2008-01-24 | 520-07-5186 | 2005-12-01 | 36000 |  |  | 5415700 | 2007-06-01
Walla Walla Community College: Science & Technology building | U94, C05 | 30001452 |  |  |  | 2020-06-10 | 16044 |  |  | 7586567 | 2022-12-01
Wenatchee Valley College: Anderson Hall Replacement | H09 | 051852 |  | 2008-01-23 | 520-07-5191 | 2005-07-01 | 80000 |  |  | 13868000 | 2007-06-01
Wenatchee Valley College: Music & Arts Center | J27 | 30000119 |  | 2014-07-31 | 497-09-5216 | 2011-05-17 | 24567 |  |  | 7794513 | 2013-05-01
Whatcom Community College Learning Commons | S16/U11 | 30000138 |  |  |  | 2017-07-13 | 65328 |  |  | 21974405 | 2021-06-30
Yakima Valley Community College: Brown Dental Clinic Rnv. | I34 | 20081317 |  | 2009-12-01 | 520-07-5274 | 2008-07-16 | 14773 |  |  | 3258000 | 2009-07-14
Yakima Valley: Glen/Anthon Hall Replacement | H69 | 041207 |  | 2007-12-22 | 520-07-5187 | 2005-08-04 | 95668 |  |  | 20516000 | 2007-11-14
Yakima Valley Community College: Palmer/Martin Replacement | J29/S05 | 30000121 | S05-L321 | 2017-01-27 | 3-15-5116 | 2013-09-25 | 41257 |  |  | 14984987 | 2019-06-30
Yakima Valley: Raymond Hall Renovation | H30 | 061325 |  | 2008-12-22 | 520-07-5234 | 2007-07-31 | 36915 |  |  | 3088000 | 2008-08-01
* If MACC not provided in Major Project Status Reports, C-100 info used