## QuickStartGuide
Major Project Report
Quick Start Guide
BACKGROUND INFORMATION
The Final Project Close-out Report requirement was implemented in the 2013-15 biennium as part of the recommendations in the 2009 JLARC report, “Evaluation of the Accuracy of Capital Project Cost Estimates.” This requirement is for agencies to submit the report to OFM at project completion to compare the scope and estimate from the predesign stage with the final scope and actual cost after construction as well as the estimate as the project was funded.
RCW 43.88.160 requires OFM to submit an annual report to the Legislature on the status of all appropriated capital projects (including transportation projects) that show significant cost overruns or underruns. As these projects are completed, agencies must provide OFM with a final summary showing estimated start and completion dates of each project phase compared to actual dates, as well as estimated costs of each phase compared to actual costs. OFM uses the information collected in the Final Project Close-out Report to make its annual report to the Legislature.
Agencies administering a major capital project or projects specifically identified for this reporting requirement by OFM or the Legislature must submit a detailed Major Project Status Report to OFM and the legislative fiscal committees each December 31 and July 1.
GENERAL INFORMATION
This comprehensive reporting tool merges the Major Project Status Report and the Final Project Close-Out Report. This is to generate consistency in reported data as required by OFM, the Legislature, and state statute; especially as it pertains to comparing cost estimates at predesign approval, cost estimates as projects are currently funded, and the actual costs at project completion.
Please contact your assigned OFM Capital Budget Analyst if you have any questions regarding this tool.
INSTRUCTIONS
1) | Blue cells are available for data entry.
2) | Select the type of report you will be submitting in cell B2. Select "Major Project Status Report" if your report is to fulfill the semi-annual requirement to update OFM and the Legislature on the status of your project. Select "Final Project Close-Out Report" if your project is complete.
3) | In the funding section, please include all funding sources for the project by phase. Identify the fund number and name (for example: "06X - Building and Tuition Acct"). Identify all local and alternative funding sources and all OFM authorized transfers from other projects. Insert rows where necessary.
4) | Cost and other variances can be compared three ways: 1) Estimates at Approved Predesign to Estimates as Currently Funded. 2) Estimates at Approved Predesign to Actuals. 3) Estimates as Currently Funded to Actuals). Click on cell H55 to select your variance comparison.
5) | Additional information, such as number and value of change orders, is required for the Final Project Close-Out Report. Those cells will be made available when that report type is selected in cell B2.
6) | If available, photos can be added to the Photo Gallery tab for a visual representation of the status of the project. Pictures can sometimes provide a better understanding of the status of a construction project than one can get from just the schedule or expenses to date. Right-click on the stock photos and select "Change Picture" to insert your photo from a file. Captions of the photo can be made in the text box below the photo.

## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2023-25 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
December 2024
| Agency | 699
| Project Name | Everett Community College - Learning Resource Center
| OFM Project Number(s) | 30000136
Contact Information
| Name | Erica Dias
| Phone Number | 425-388-9516
| Email | edias@everettcc.edu
Project Information
| Project Description: | The new Everett Community College Library Resource Center building will provide critically needed new space for library services, the writing center, the tutoring center, the Center for Transformative Teaching and Media Services. The existing first floor space the EvCC Parks Student Union will be remodeled to accommodate programs that are in other campus buildings currently slated for demolition.
(Include a brief summary of the project and the programs it supports.)
| Project Status: | Cascade Learning Resource Center construction was completed in Spring of 2023 and the city-required frontage improvements completed September of 2023. The college had a soft opening of the building in July of 2023 and a grand opening in September of 2023. The building is now in full operation and all features are being utilized by students and staff. The building is open to the community but so far, foot traffic has been fairly minimal. The utility easement was recorded and submitted to the city on December 12 which is the final action needed in order to obtain full certificate of occupancy. Certificate of Occupancy received 1/10/24. Foot traffic has increased and the library has expanded weekend hours now.
(Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.)
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan |  |  | TOTAL | Notes
| Phase & Fund Type | Prior Expended | 2023-25 Expended | 2023-25 Remaining | 2025-27 Plan | Future Plan
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldg. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 3450202 | 0 | 0 | 0 | 0 | 3450202
| 057 - State Bldg. Const Acct | 3450202 |  | 0 |  |  | 3450202 | U90
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 40825935 | 3326157.75 | 4495843.05 | 0 | 0 | 48647935.8
| 057 - State Bldg. Const Acct | 40825935 | 3326157.75 | 4495843.05 |  |  | 48647935.8 | C02
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 44276137 | 3326157.75 | 4495843.05 | 0 | 0 | 52098137.8
Details
| Construction Type | Libraries |  | Project Administered By |  | DES
| % of Bldg. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 70000 | 70000 |  | -70000
| Usable Sq Ft (USF) |  |  | 47600 | 45500 |  | -45500
| Space Efficiency (USF/GSF %): |  |  | 68% | 65%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): | [5 empty] | 0
| MACC/Bid Award COST/GSF |  |  | 443.6593 | 482.5266
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 511.1203 | 558.2724
Milestone Dates
| Predesign Complete |  |  | 2018-12-01 | 2019-03-01 | 2019-02-25 |  | OFM approved
| Start Design |  |  | 2019-01-01 | 2019-04-01 | 2019-02-26
Bid Due Date
| Notice to Proceed |  |  | 2021-07-01 | 2021-07-01 | 2021-07-15 | 0.5 mo.
| Substantial Completion |  |  | 2023-04-01 | 2023-01-01
Final Acceptance/Project Close-out Date
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
| Acquisition Costs Total |  |  | 4000000 | 4000000 |  | -4000000
Consultant Services
| Pre-Schematic Design Services |  |  | 366162 | 369110 | 257364 | -111746
| AE Basic Service Fee - Construction Documents |  |  | 1460335 | 1558511 | 1822184 | 263673
| Extra Services - Pre-Bid |  |  | 1488816 | 1880497 | 1191801.87 | -688695.13
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 687948 | 731078.82 | 636693 | -94385.82
| Other Services - Post Bid |  |  | 222241 | 227890 | 0 | -227890
| Design Services Contingency |  |  | 439240 | 471953 |  | -471953
| Consultant Services Total |  |  | 4664742 | 5239039.82 | 3908042.87 | -1330996.95
Construction
| Site Work |  |  | 4726612 | 5591260 | 490865.39 | -5100394.61
| Related Project Costs |  |  |  |  | 1385692 | 1385692
| Facility Construction |  |  | 26329537 | 28185603 | 37077062.42 | 8891459.42
| Maximum Allowable Construction Cost (MACC) Subtotal |  |  | 31056149 | 33776863 | 38953619.81 | 5176756.81
| Construction Contingencies |  |  | 1558638 | 1814271 |  | -1814271
| Non-Taxable Items | [5 empty] | 0
| Sales Tax |  |  | 3163635 | 3487932 | 3856408.38 | 368476.38
| Design-Build Costs | [5 empty] | 0
0
| Construction Contracts Total |  |  | 35778422 | 39079066 | 42810028.19 | 3730962.19
Other Project Costs
| Equipment |  |  | 2574744 | 2642590 | 1422181.04 | -1220408.96
| Art Work |  |  | 155281 | 259197 | 259197 | 0
| Project Management |  |  | 183048 | 187699 |  | -187699
| Other Costs (describe) |  |  | 1738811 | 691068 | 340697 | -350371
| Other Project Costs Total |  |  | 4651884 | 3780554 | 2022075.04 | -1758478.96
| Total Project Costs |  |  | 49095048 | 52098659.82 | 48740146.1 | -3358513.72
Additional comments:
Other costs consist of legal notices & permit fees. Wa Arts Commission June 2023 - artwork installed May 2023 Leo Berk

## Photo Gallery (2)
Photo Gallery
Roofing Complete
Grand Stairs installed
Exterior insulation with vapor barrier
Hollow Metal frame in Room 104
Overall site view on 3/1/2022 - Exterior Framing started on 1st floor
Overall site view on 4/1/2022 - Exterior Framing on going
Overall site view on5/2/2022- weather barrier complete and window frames installed
Overall site view on 6/17/2022 - Glasing is ongoing and brick is finished at the west side and starting on the east

## Photo Gallery (hidden)
Photo Gallery
Right-click on picture above to change picture to photos of the project.
Triple-click on this text to change the caption.
Picture caption here.
Picture caption here.
Picture caption here.
Picture caption here.
Picture caption here.
image credit: www.bownegroup.com

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | January 2025 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | February 2025
Art galleries |  |  | 2006 | Other (explain below) | March 2025
Auditorium with stage |  |  | 2007-09 |  | April 2025
Auditorium without stage |  |  | 2008 |  | May 2025
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | June 2025
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | July 2025
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | August 2025
Computer rooms |  |  | 2012 |  | September 2025
Convention facilities |  |  | 2013-15 |  | October 2025
Courthouses |  |  | 2014 |  | November 2025
Day care facilities |  |  | 2015-17 |  | December 2025
Detention/correctional facilities - maximum |  |  | 2016 |  | January 2026
Detention/correctional facilities - min & max |  |  | 2017-19 |  | February 2026
Dining halls/institute |  |  | 2018 |  | March 2026
Dormatories |  |  | 2019-21 |  | April 2026
Emergency generator facilities |  |  | 2020 |  | May 2026
Exposition building |  |  | 2021-23 |  | June 2026
Extended care facilities |  |  | 2022 |  | July 2026
Farm structures |  |  | 2023-25 |  | August 2026
Fire and police stations |  |  | 2024 |  | September 2026
Fish hatcheries |  |  |  |  | October 2026
Greenhouses |  |  |  |  | November 2026
Guard towers |  |  |  |  | December 2026
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")