## QuickStartGuide
Major Project Report
Quick Start Guide
BACKGROUND INFORMATION
The Final Project Close-out Report requirement was implemented in the 2013-15 biennium as part of the recommendations in the 2009 JLARC report, “Evaluation of the Accuracy of Capital Project Cost Estimates.” This requirement is for agencies to submit the report to OFM at project completion to compare the scope and estimate from the predesign stage with the final scope and actual cost after construction as well as the estimate as the project was funded.
RCW 43.88.160 requires OFM to submit an annual report to the Legislature on the status of all appropriated capital projects (including transportation projects) that show significant cost overruns or underruns. As these projects are completed, agencies must provide OFM with a final summary showing estimated start and completion dates of each project phase compared to actual dates, as well as estimated costs of each phase compared to actual costs. OFM uses the information collected in the Final Project Close-out Report to make its annual report to the Legislature.
Agencies administering a major capital project or projects specifically identified for this reporting requirement by OFM or the Legislature must submit a detailed Major Project Status Report to OFM and the legislative fiscal committees each December 31 and July 1.
GENERAL INFORMATION
This comprehensive reporting tool merges the Major Project Status Report and the Final Project Close-Out Report. This is to generate consistency in reported data as required by OFM, the Legislature, and state statute; especially as it pertains to comparing cost estimates at predesign approval, cost estimates as projects are currently funded, and the actual costs at project completion.
Please contact your assigned OFM Capital Budget Analyst if you have any questions regarding this tool.
INSTRUCTIONS
1) | Blue cells are available for data entry.
2) | Select the type of report you will be submitting in cell B2. Select "Major Project Status Report" if your report is to fulfill the semi-annual requirement to update OFM and the Legislature on the status of your project. Select "Final Project Close-Out Report" if your project is complete.
3) | In the funding section, please include all funding sources for the project by phase. Identify the fund number and name (for example: "06X - Building and Tuition Acct"). Identify all local and alternative funding sources and all OFM authorized transfers from other projects. Insert rows where necessary.
4) | Cost and other variances can be compared three ways: 1) Estimates at Approved Predesign to Estimates as Currently Funded. 2) Estimates at Approved Predesign to Actuals. 3) Estimates as Currently Funded to Actuals). Click on cell H55 to select your variance comparison.
5) | Additional information, such as number and value of change orders, is required for the Final Project Close-Out Report. Those cells will be made available when that report type is selected in cell B2.
6) | If available, photos can be added to the Photo Gallery tab for a visual representation of the status of the project. Pictures can sometimes provide a better understanding of the status of a construction project than one can get from just the schedule or expenses to date. Right-click on the stock photos and select "Change Picture" to insert your photo from a file. Captions of the photo can be made in the text box below the photo.

## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2023-25 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
December 2024
| Agency | 699
| Project Name | Spokane Falls Community College Fine and Applied Arts Replacement
| OFM Project Number(s) | 30001458
Contact Information
| Name | Clinton Brown
| Phone Number | 509-533-4899
| Email | clinton.brown@ccs.spokane.edu
Project Information
| Project Description: | Project to replace the Fine Arts Building and the Photography Building on the SFCC Campus with a single structure. The building will contain classrooms, computer labs, faculty offices, student study spaces, and the specialized lab type space necessary for the instructional programs: Photography, media, drawing, painting, sculpture, ceramics, print-making, jewelry making, art history and appreciation, and more. Spaces will include studios, dark room(s), exhibition hall/galleries, and storage.
(Include a brief summary of the project and the programs it supports.)
| Project Status: | Project reached substantial completion on 8/6/24, though legal completion still remains at 8/5/23. Extensive punch list remains as well as non-conforming work which have now transcended the required date for Final Completion. Separate contractors have been brought in to complete the work refused by the original contractor.
(Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.)
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan |  |  | TOTAL | Notes
| Phase & Fund Type | Prior Expended | 2023-25 Expended | 2023-25 Remaining | 2025-27 Plan | Future Plan
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldg Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 2827000 | 0 | 0 | 0 | 0 | 2827000
| 057 - State Bldg Const Acct | 2827000 |  |  |  |  | 2827000 | U40
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 22884980 | 11424359.05 | 5032660.95 | 0 | 0 | 39342000
| 057 - State Bldg Const Acct | 20000000 | 0 | 0 |  |  | 20000000 | A20
| 057 - Other State Funding | 2884980 | 11424359.05 | 5032660.95 |  |  | 19342000 | C06
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 25711980 | 11424359.05 | 5032660.95 | 0 | 0 | 42169000
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldg Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Bid-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 57693 | 59837 | 59837 | 0
| Usable Sq Ft (USF) |  |  | 40385 | 41886 | 41886 | 0
| Space Efficiency (USF/GSF %): |  |  | 70% | 70% | 70% | 0%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 35274 | 35274 |  | -35274
| MACC/Bid Award COST/GSF |  |  | 430.7322 | 473.3207 | 441.248 | -32.0727
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 515.5003 | 541.8356 | 490.2491 | -51.5864
Milestone Dates
| Predesign Complete |  |  | 2018-11-01 | 2019-01-01 | 2019-01-07 | 0 mo.
| Start Design |  |  | 2018-12-01 | 2019-02-01 | 2019-04-24 | 2.5 mo.
| Bid Due Date |  |  |  |  | 2020-06-30 | 1446 mo.
| Notice to Proceed |  |  | 2020-04-01 | 2020-07-22 | 2020-08-06 | 0.5 mo.
| Substantial Completion |  |  | 2022-01-01 | 2024-09-01 | 2024-08-06
| Final Acceptance/Project Close-out Date |  |  |  | 2024-10-05
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
| Acquisition Costs Total | [5 empty] | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 434108 | 193950 | 207504 | 13554
| AE Basic Service Fee - Construction Documents |  |  | 1278644 | 1598130 | 1505078 | -93052
| Extra Services - Pre-Bid |  |  | 651895 | 1727947 | 1442152 | -285795
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 600801.0624 | 634427 | 730884 | 96457
| Other Services - Post Bid |  |  | 489183 | 401533 | 330687 | -70846
| Design Services Contingency |  |  | 357044 | 474009 | 0 | -474009
| Consultant Services Total |  |  | 3811675.0624 | 5029996 | 4216305 | -813691
Construction
| Site Work |  |  |  | 1863653 | 2278746 | 415093
| Related Project Costs |  |  |  | 754497 | 3332216 | 2577719
| Facility Construction |  |  | 24850230 | 25703943 | 20791994 | -4911949
| Maximum Allowable Construction Cost (MACC) Subtotal |  |  | 24850230 | 28322093 | 26402956 | -1919137
| Construction Contingencies |  |  | 2485023 | 1422690 | 491338 | -931352
| Non-Taxable Items |  |  |  |  | 0 | 0
| Sales Tax |  |  | 2405503 | 2677031 | 2440743 | -236288
0
0
| Construction Contracts Total |  |  | 29740756 | 32421814 | 29335037 | -3086777
Other Project Costs
| Equipment |  |  | 3033971 | 2650819 | 2107309 | -543510
| Art Work |  |  | 124251 | 379426 | 378675.47 | -750.53
| Project Management |  |  | 326353 | 569630 | 439157 | -130473
| Other Costs (describe) |  |  | 1238752 | 239455 | 344500 | 105045
| Other Project Costs Total |  |  | 4723327 | 3839330 | 3269641.47 | -569688.53
| Total Project Costs |  |  | 38275758.0624 | 41291140 | 36820983.47 | -4470156.53
Additional comments:
Demolition: UFI A06505 Fine Arts 24,873 gsf / UFI A09540 Photography 10,401 gsf Wa Arts Commission: 12/15/23: - Artwork was successfully installed in September of 2023. Note: The artist could be held responsible for potential project delays/costs due to the GC receiving artwork much later than anticipdated as well as the artist not being available for timely supervision of the installation. Additionally, GC provided support for unloading pieces from shipping containers that was unforeseen and not accommodated by the artist or ArtsWa. - SFCC/CCS Administration has named the new facility ska-hét (anglicized) or sƛ̓x̣etkʷ (Salish) - meaning "rapids" or "fast water." This was the word that the tribes used to talk about Spokane Falls as well as a generalized name for the entire Spokane River. SFCC collaborated with the Spokane Tribe. NOTE: Payment to Fraudulent account occurred on 7/31/23 in the amount of $1,001,457.65. A second payment for the same amount was paid to the contractor for construction services associated with Project 2018-063 I (3-3) Invoice 21R. The additional expenditure is not accounted for in the above totals. Work continues with the Attorney General and Federal agencies to recover these fraudulant expenses. A portion of these funds have been recovered as of November 2024.

## Photo Gallery (4)
Photo Gallery
Main Lobby looking west
Main Lobby looking west
Exterior South Elevation
Exterior Southeast Elevation
Print Making Shop
South Elevation
Lecture Room

## Photo Gallery (3)
Photo Gallery
East Entrance Walkway looking northeast
South elevation, Art Glass on second floor
North patio and lobby glass looking east
Lobby looking north
Lobby looking east
South Elevation, Main Entrance
South Elevation, Fire lane looking west

## Photo Gallery (2)
Photo Gallery
Slab on Grade Pour - East Wing, June 2022
Slab on Grade Pour - East Wing, June 2022
Old Wood Water pipe unearthed on site
Slab on Grade Pour - West Wing, June 2022
Steel Erection Started, July 2022
Steel Erection Progressing, July 2022
Steel Erection Topping Out, August 2022
Slab on Metal Deck-MEP Rough-In, September 2022
Steel Stud Framing, West Wing, 1st Floor, September 2022
Mechanical Rough-In On-Going, October 2022
Exterior Enclosure/Roof Deck - West Wing, November 2022
Design Students, Tour of Site, 2nd Floor View of River Valley, November 2022
Cold Weather, tenting/heating, December 2022

## Photo Gallery-Art(5)
Photo Gallery
Jill Anholt art as viewed from interior
Jill Anholt 2nd interior view

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | January 2025 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | February 2025
Art galleries |  |  | 2006 | Other (explain below) | March 2025
Auditorium with stage |  |  | 2007-09 |  | April 2025
Auditorium without stage |  |  | 2008 |  | May 2025
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | June 2025
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | July 2025
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | August 2025
Computer rooms |  |  | 2012 |  | September 2025
Convention facilities |  |  | 2013-15 |  | October 2025
Courthouses |  |  | 2014 |  | November 2025
Day care facilities |  |  | 2015-17 |  | December 2025
Detention/correctional facilities - maximum |  |  | 2016 |  | January 2026
Detention/correctional facilities - min & max |  |  | 2017-19 |  | February 2026
Dining halls/institute |  |  | 2018 |  | March 2026
Dormatories |  |  | 2019-21 |  | April 2026
Emergency generator facilities |  |  | 2020 |  | May 2026
Exposition building |  |  | 2021-23 |  | June 2026
Extended care facilities |  |  | 2022 |  | July 2026
Farm structures |  |  | 2023-25 |  | August 2026
Fire and police stations |  |  | 2024 |  | September 2026
Fish hatcheries |  |  |  |  | October 2026
Greenhouses |  |  |  |  | November 2026
Guard towers |  |  |  |  | December 2026
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")