## Slide 1: DG3 LESSONS LEARNED
Report Compiled by ctcLink Project Management Office (PMO) Team
July 2020

## Slide 3: Ctclink quality gates & milestones
Ctclink quality gates & milestones
DEPLOY
Lessons
Learned
TRANSITION
End-User Training
User Acceptance Testing
Production Go/No Go Decision
Cutover Mitigation Planning
Determine Exception
Solutions
Update BP Flows
Update CEMLIs
Update Configuration
Functional Testing
Prepare QA
Environment
Prepare Parallel
Environment
CONSTRUCT
Parallel Testing
System Integration Testing
Convert and
Validate Data
Production Cutover Planning
Production Cutover
Security Matrix
Mapping
Production Environment Prep
STRUCTURE
Global Design Adoption (GDA)
Business Process Fit/Gap (BPFG)
Update BP Flows
Local Configuration
UAT Test Definition
UAT Materials Build
Identify Exceptions
Design Extensions
Prepare or Update
Test Scripts
Training Materials
Analysis/Build
Map Supplemental Systems Data
Go/No Go Decision
Milestone Sign-Off
GO LIVE
Finalize Local Configuration Guides
Project Planning (Checklists & Templates)
Security Redesign (DG2 only)
Build PeopleSoft Environments
Chart of Accounts Redesign (DG2 only)
Performance Testing
Organizational Change Management Assessments Begin
OCM Assessment, Activities & Deliverables for Colleges & SBCTC
College Project Charter Resource Plan & Budget Plan Deliverables Legacy BP Mapping Initial Supplemental Systems Analysis Change Impact Analysis 25% | GDA and BPFG Participation Supplemental Systems Data Mapping Initial Config Guides Sign-Off UAT Definition Sign-Off Change Impact Analysis 50% | Design Requirements Sign-Off Security Matrix Mapping Data Validation Sign-Off Change Impact Analysis 75% | OCM Readiness Checklist UAT Sign-Off End-User Training Policy/Procedures Updated Cutover Plans, Legacy Shutdown Procedures Change Impact Analysis 100% | College Cutover Plan Go/No Go Sign-Off Milestone Sign-Off Config Guides Sign-Off College Lessons Learned Rev. 2019-03-05
Legacy System Shutdown Procedures in Place
GATE 1 | GATE 2 | GATE 3 | GATE 4 | GATE 5
INITIATION
Pre-User Acceptance Testing Training
Production Validation
GATE 1 PEER REVIEW
Start Change Impact Analysis & Change Action Plan

## Slide 4: Lessons learned Sessions
Meetings | Date Completed
DG3-A Conversion Approach Lessons Learned to Implement for DG3 Go Live (ctcLink Team Only) | March 12, 2020
DG3-A College Lessons Learned (Lower Columbia & Olympic) | April 23, 2020
DG3-B College Lessons Learned (Cascadia, Pierce & Peninsula) | June 15, 2020
ctcLink Pillar Specific Lessons Learned Sessions | June 2020
Feedback from SBCTC Support Areas | June 2020

## Slide 5: Global design adoption (gda)
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Student Financials (SF) GDA Videos | Videos created for DG3 to provide better explanation for SF concepts: item types, account codes, cross-walks. | Videos were utilized for DG4. | Student Financials | Completed
SME Comprehension | SMEs comprehension and understand the global configuration through GDA. | Quiz or surveys provided after GDA. Timing of the survey is key so SMEs do not confuse if this is for GDA or BPFG. | HCM & FIN | Need evaluation to tracking comprehension and completion
SME Completion | Important to track completion of the GDA courses before the BPFG sessions. | Need a proper way of tracking completion before the BPFG sessions. | HCM & FIN | Completed GDA reports in cDR; project coordinators verify data on BPFG registration sheets to help inform PMs
Emphasize Concepts | Basic fundamentals from GDA courses and PS Fundamental courses in order to help SMEs retain it in their knowledge bank and understand PS business processes. | Inform PMs to have SMEs refresh on PS fundamentals. Team will also emphasize the concepts during BPFG sessions. | HCM & FIN | Team can incorporate into BPFG
Review Assessment in GDA | What data is provided? | We need to review the data that we get from assessment. | FIN | Something team can do and incorporate into BPFG
Business Processes | Local BP are not well understood or mapped out. | Emphasize the importance of completing local business process maps with College PMs prior to GDA and BPFG. | FIN | Something team can do and incorporate into BPFG

## Slide 6: College suggestions for GDA
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Tracking SME completion of courses | Was challenging to track GDA requisite completion before SMEs attended BPFG sessions. Tracking was a challenge for PM; hard to know where folks were. | Confirm tracking tool process/reporting system. | Lower Columbia, Pierce & Peninsula | Completed, GDA reports in cDR
Sessions | Confusion on purpose/intent | More upfront in communications. | Olympic | Completed, incorporated into PM Prep Sessions
Canvas | Verifying courses in Canvas was time consuming | "List?" like Angela provided | Cascadia | Completed, GDA reports in cDR, provide PMs with bi-weekly deployment group report
Crash course/PS fundamentals | PS Fundamentals not sufficient intro to GDA | workshop to be oriented to terminology | Cascadia | Completed by Training team based on DG4 feedback

## Slide 7: Business process fit/gap (BPFG)
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Dual Processing Homework | Improvements in a couple of dual processing cross-walks and EPC-Academic Plan session. | Two cross-walks were prep-populated with data helped the colleges. EPC-Academic Plan (additional session) was held for DG4 to provide more clarity. | FA | FA to prepopulate similar to HCM
Volume of FA Sessions | FA sessions were combined. | This was implemented in DG4; more combined FA sessions. | FA | Completed, implemented for DG4
Dual Processing BPFG Guides | Received feedback from DG3. | Made improvements to the BPFG guides for DG4. | FA | Completed, implemented for DG4
HR Core & Bio/Demo | Team has re-looked at this approach to not have these as two separate sessions. | DG5 this will be a combined session to connect job data with other elements in bio/demo. | HCM | Completed, implemented for DG4
Analysis of all HCM BPFG Sessions | Team has reviewed the homework process & streamlined the data: templates, pre-populate as needed, assignment. This would make it easier for the colleges to submit their homework. | Two new approaches: reviewed legacy data to prep-populate the data (example: contracts) so the colleges can review their data & pulled data from legacy to pre-populate the data so the colleges can review their existing data and edit the data. | HCM | Completed, implemented for DG4

## Slide 8: BPFG CONTINUED
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Faculty WorkLoad & Payroll BPFG Sessions | Colleges have provided positive feedback for these sessions. FWL session is a week long with a lot of interaction and engagement with the SMEs. | These are two great session models for other HCM sessions. Homework is completed during the sessions and colleges found this to be very easy and helpful. Remote or virtual session for the FWL session will need to have breakout sessions as part of the mode of delivery. Colleges will also be responsible for engaging remotely and having the correct technology tools. | HCM | Completed, implemented for DG4
Dual Processing Session | EPC and Plan codes and mapping for dual processing. | Help the colleges understand what we do in CS Core and collaborate with FA team so what we are asking the colleges for is accurate. | CS | Completed, implemented for DG5
SF Team Cross-Modular Facilitation | SF team members were not prepared to delivered some BPFG sessions/content. | Work with new SF Pillar PM and discuss ways to better prepare presenters. | CS | Completed, implemented for DG5
General BPFG Overview session for FIN | Similar to the data cycle validation walk through. | Idea is to create a video or presentation for FIN. | FIN | Completed, implemented for DG4

## Slide 9: College suggestions for BPFG
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
SME Knowledge; Prep for BPFGs | Even though concepts were presented, SMEs had difficulty following and putting it into practice because didn't have context to go back to. | NA | Pierce | SMEs required to take GDA and track comprehension and completion
Difficulty managing areas/times | Competing priorities across campus (councils, etc.). | NA | Pierce | Completed, we are providing better tracking for PMs
Subject area scheduling | Conflicting schedules of BPFG for cross-pillars and within FIN; SF and grants/contracts on same day/time; HR core, Time & Labor. | Small staff means everyone is working multiple modules, pillars. | Pierce | Completed, we have where possible scheduled with no overlap and built schedules with DG5 and DG6 to baseline early
Cross-Pillar Sessions | SMEs need to understand processes across pillars. | Provide more clarity around attendees on specific sessions, especially cross pillar. | Pierce | Completed, we have scheduled more Cross-Pillar sessions to address issue
Shared responsibility for learning | Learning environment to test processes, learn as you go. | Colleges should involve people who do the end processes; not just SMEs or super SMEs. | Peninsula & Pierce | Completed, provided to DG4, DG5, and DG6 just following BPFG and Security build

## Slide 10: College suggestions for BPFG, CONT’D
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Future State Knowledge/SME Continuity | SMEs making decisions without context. |  | Cascadia | Updated BPFG content to help with this and weekly sessions to address follow-up questions
Gap between BPFGs and Go-Live | Concern of so much time has passed between decisions made during BPFGs and go-live. | Revisit decisions made prior to go-live | Olympic & Pierce | We can include reviews as part of UAT
Assignment of attendance per BPFG falls to one person | Need more clarity about who to attend for decision-making and attendance; Conversation and learning from other colleges beneficial. | Better decision process to help colleges decide who to attend, cross-pillar representation | Olympic & Pierce | Completed, this is part of work College Advisor is doing to cross GDA and BPFG attendees to homework
Cross-Pillar Session | Business processes overlap. Need a session(s) for overlap. | Invite cross-pillar/module SMEs | Lower Columbia & Pierce | Completed, this has already been incorporated into the DG5 schedule
Session Scheduling | We had a situation where same person was needed to be in 2 places at once for FWL and Curriculum Management BPFGs. | Not overlapping sessions even if in different pillars. | Olympic | Completed, we have taken this into consideration with future deployments and built schedules with minimal if any overlap

## Slide 11: Data conversion & validation
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
SF Conversion Approach | Approach needs to be more detailed (with micro-subset level). | Cycle #2 could be macro level and Cycle #4 would be micro level detail for DG4. | SF | Completed per recommendation
Priority Logic for CS/Bio Demo | Priority logic (trumping rules). DG3 first time we used this conversion logic. | Will look at the approach for DG4 and enhance the conversion logic. | CS Core | Completed, cycle 1 removed and incorporated into cycle #2 for better understanding
Enrollment Conversion | Updated conversion logic that helped reduce go live errors for enrollment and reporting. | This was updated from DG2 for DG3 and then again modified from DG3A to DG3B. | CS Core | Completed and implemented for future deployment groups
Program/Plan Discontinuation | Updated conversion logic that helped reduce go live issues for reporting. | Update was made from DG3A for DG3B | CS Core | Completed and implemented for future deployment groups
AR/SF Cross Pillar | We have improved in this areas and had joint team sessions to review the data together for DG3. | Both teams will need to review data errors and make improvements for the AR/SF data conversion cycles. Legacy data also needs to be reviewed closely by the colleges. | FIN | Done, and implemented for future DG
Recording Data-Related Follow-Up Sessions | This was beneficial to record the sessions to show a process. | Continue to do this for DG4. | FIN | Done, and implemented for future DG

## Slide 12: Data conversion & validation, cont’d
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Grants & Projects Cross-Walks | Reframe assignments or data requests. | Team will be enhancing this for DG4 Cycle 3. | FIN | FIN team will be working on these improvements for DG4.
Operational Budget Line Conversion | At Go-Live, general budget line is not available as part of the conversion program. | After GL conversion, develop and run the program to get the journal line in to the budget line so colleges can review it and load it or have our team load it. | FIN | FIN team will be working on these improvements for DG4.
PCard Multiple Proxy User Assignment | Colleges have multiple proxy list. CI template does not work, so manual work is needed to add more than one user. This impacts data validation activities for the team. | Revisit CI template. | FIN | FIN team will be working on these improvements for DG4.
Grants & Projects Conversion | Currently, run an excel to CI before the conversion program can begin and with the number of colleges it becomes longer and longer. | Team has started to test out and move tables. More research is needed, idea is to have DMS script or have this built by colleges in PRD. Needs to be reviewed for DG4 in Cycle 3. | FIN | FIN team will be working on these improvements for DG4.

## Slide 13: Data conversion & validation, cont’d
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
HR Resource | Identified a resource to access the legacy data. | This was an enhancement the team made to improve the approach. | HCM | Done, as part of their preload of HW
HCM Data Validation Guides | Guides needed to be improved to provide guidance to the colleges. | Testing coordinators have helped change this information to a better format in Canvas. | HCM | Done, and implemented for DG4
HCM Legacy Data Clean-Up | Data errors for SMEs are not clear. | Team is providing better information on legacy data cleansing instructions. | HCM | Done, College Advisor has worked on this

## Slide 14: College suggestions for data conversion & validation
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Supplemental Systems | Everything related to this was left up to the colleges; how to make them work. Did not have a good system to bring data down to ctcLink. | Having instructions on how to bring information into new system would be extremely helpful. Had to find own way to make the information convert the way needed; was a great deal of work. (DataLink) | Cascadia | The team will consider this lessons learned.
Timing of resources | Local Configuration Guides - received mid-week of the week before go-live. | Would have liked more time to fully review. | Lower Columbia | We will provide this information well in advance of go-live data validation activities.
Data validation workload | Data validation periods are very short for the volume of data being reviewed. There is also a huge gap from when the snapshot is taken and when data is validated. This makes it difficult to validate that configuration changes and clean-up efforts have been successful. | NA | Lower Columbia | We have looked at the timing and recognize the timing is very short in duration. We will do our best to provide the colleges adequate time.

## Slide 15: Project plan/schedule
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Payroll Parallel | Steps and ownership were not clear in the plan. Communication to SMEs of what environments and their purpose. Parallel testing kept sliding in the schedule | Align tasks and ownership for payroll parallel. Needs to be scheduled about a month prior (2 major tasks: building test environment, provisioning accounts for user access) | HCM & Legacy | Changed approached for DG4 and beyond. Coordinated work effort with testing team. Timeline and materials have been aligned to begin earlier in the schedule.
Communicate Legacy Shut Down | Legacy Manager had to abort users on Friday AM on 5/8/2020. | Need better communication | Legacy | For DG4, we will include the communication activities in the Project Plan and Cutover Schedule.

## Slide 16: College suggestions for project plan/schedule
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
dataLink | Problematic because live data not available | Colleges sign MOU | Lower Columbia, Olympic | Data Services is coordinating with the colleges for an instance for data that the colleges can use to test their integration and downstream processes.
Timeline Concerns / Compression | Timelines changed but the colleges were not given additional time. Many activities were at high peak times for the college making it difficult to engage more people. | NA | Pierce | The project team makes every effort to not compress schedule and overlap activities. Unfortunately, based on unknown risks/issues there has been compression of the schedule.

## Slide 17: User acceptance testing (UAT)
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
FA UAT /Dual Processing | SIT was not completed and configuration was missing or not moved over. Dual processing was not completed and SMEs did not understand what they are testing. Huge impact for post-go live with SMEs. | FA team will work better as a team to make sure everyone is on the same page to ensure that SIT is complete. FA team will work closely with DG4 SMEs in this testing engagement and provide better data knowledge transfer and understanding what they are testing. | FA | We have re-aligned our testing team to have more quality controls around SIT, UAT and parallel testing.
UAT Approach | Pre-UAT or Just in Time Training Concept for DG2 has been incorporated in the testing approach. | This will be incorporated in to the UAT approach for DG4. Project team will be facilitating the morning session. | HCM | Completed, implemented for DG4
AWE (Approval Workflow Engine) Testing | College SMEs struggled with AWE concept and visualize this once they are live in PS. Lack of real users involved in this testing process. | Provide better information, have their security configured and have additional SMEs to be able to participate in the approval process. | FIN | Encourage more college users to participate in testing activities who will be approving.
SF to GL Testing (Parallel) | Scope and it can be mapped out better. | We need to discuss this for DG4 with both teams. | FIN | Joint effort by the teams to coordinate this effort.

## Slide 18: College suggestions for UAT
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Timing of Training/Testing | Didn't have enough SMEs so were learning while testing, this was security-related as well. Didn't know if people had correct permissions | Visibility of and training on MetaLink would be helpful. Need overview of test processes just prior to testing. Had been too long since BPFG/training sessions to understand requirements. | Cascadia | Based on DG2/3 feedback changed approached.
Sandbox | No “sandbox” for finance with real information to test or even for validation. |  | Pierce | Solution Validation Environment; timed with security work and their data was better aligned and available for DG4.
Employee and Manager Self Service in UAT | Environment suggestion | Having ESS and MSS set up in UAT would have made it helpful for training employees prior to go-live. | Pierce | ESS and MSS are included in the enhanced self-paced training approach prior to UAT. During UAT, additional knowledge transfer will be addressed.
OTM | Be proactive in OTM tickets | During UAT testing, stay on top of OTM tickets. Make sure you are not waiting for answers or help. | Lower Columbia | Engage more with the testing manager.

## Slide 19: Security
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Validation Query Security | Data was classified as highly sensitive data and would not return results. | Communicate with the PMs the options for pulling that data. | CS Core | We have ensured in our migration approach to prepare for UAT that the CS Core queries are appropriately migrated with the correct security.
Local Configuration Guides | We changed our method for the configuration guides and it provided insight that the local security roles were not tested. | We will need to work with our support team to maintain the security role definitions needed to access the local config guides. | CS Core | The local configuration guides are posted in the ctcLink Reference Center for the colleges so they have access to pull the values as needed during the implementation and post implementation. Security documentation is also located in the ctcLink Reference Center.

## Slide 20: College suggestions for Security
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
PM Perspective | Learning process - to be able to train team so they are able to do tasks. | Making sure it's resourced properly. | Olympic | Providing knowledge transfer and identifying college roles earlier.
Queries | Queries and access, knowing correct security roles, how they work and how to pull the data needed when we don't know where the data is housed | Improved security training and resources | Olympic | Encourage colleges to take the Data Services query trainings earlier and often.
Security communications | Need to be able to communicate quickly and directly to assist with security | Establish a Security Admin list | Lower Columbia | We will work with the colleges for their list and provide it to the Support team.
SACR preferences and settings | SACR preferences for employees; how to share and document levels of access | Can this be added to QRGs? | Pierce | We have added this to the security documentation in the ctcLink Reference Center. We will review this information for the QRGs.
Security validation | Double check roles | Be sure to audit Department Managers, Speed Types, and Item Types, especially changes requested after the last cycle of data validation. LCC’s changes were not reflected and we had a lot of random errors. We had hundreds of Department codes with the wrong manager. Speed Types and Item Types were not updated based on the last info we provided. | Lower Columbia | For DG4, this will be incorporated and tested in UAT.

## Slide 21: College suggestions for security, cont’d
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Security validation time | Establish processes for security approvers | Ensure that there is adequate time in the schedule to validate security role assignment in the solution validation environment (SVX for DG3) | Lower Columbia | For DG4, the security work has been kicked off well in advance (7 months) of go-live.
Establish your local processes | Who is going to reset security questions for employees? Who is going to do that for students? How will you verify the identity of the person making the request (for both employees and students)? Who needs that information, how will they get it, and where do they need it (off campus)? How are employee network accounts going to be created? How are student network accounts going to be created? How are student employee accounts going to be created? When do they need to be created in order to enter time and leave in for Payroll? Who will create them? Is there a process for HR to verify and create accounts? | Establish your local processes | Lower Columbia | We are asking the colleges to establish their Security Support Plan.
Security | Good information provided, but tight timeline | More time | Lower Columbia | For DG4, the security work has been kicked off well in advance (7 months) of go-live.

## Slide 22: Training, OCM & communications
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Go-Live Validation Activities during Dry Run | Clear naming, clear expectations and passwords for SMEs, clear process, OTM/logging issues, document for our team to report to colleges, guides posted early with correct passwords and in one location |  | ctcLink PMO | We will review the approach for DG4.
Dual Processing Business Process guides on the ctcLink reference center | Received feedback from DG3. | Made improvements to the business guides for DG4. | FA | Completed for DG4.
SME contact list | Idea to share knowledge for BPFG, data conversion, cross-walks. | Provide a list of key SME contacts for live colleges so DG4 SMEs can reach out to them for questions and clarity. | FA | We will consider this idea list.

## Slide 23: College suggestions for Training, OCM & Communications
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Training/Workshops leading up to go-live | WebEx sessions the last two weeks were awesome! | Split SMEs by college if possible? Was difficult for everyone to have a chance to ask questions | DG3 | There were sessions conducted prior to go-live and many sessions requested and conducted post go-live.
PS Fundamentals | PeopleSoft Fundamentals is very comprehensive. Would be helpful to have a less technical course with some basic PeopleSoft functions for employees such as faculty. |  | Pierce | PS Fundamentals 9.2 was completed and delivered in July 2020 to the colleges.
Local campus training guides | Recommend putting together your own user guides and providing beginner user training for all staff – how to submit leave/time. A lot of variables and nuances with time and leave reporting. |  | Pierce | Colleges can pull content from the ctcLink Reference Center to create local desktop procedures.
Inconsistent information from Project vs Support | One of the biggest issues is that the project team has told us a way to do things in ctcLink or how they will be done. But then when we work with the ERP team it is completely different. This is really difficult since we learned it one way and then are expected to do it a different way. |  | Lower Columbia | The Project team and Customer Support organization continue to align knowledge and skills.
Understand local business processes |  | Understand if your process works jointly with another person (Grants and AR) and what to expect on both sides from the other. | Lower Columbia | Colleges need to spend time discussing change impact analysis from their legacy BPs to the new ctcLink BPs and document them.

## Slide 24: College suggestions for Transition support (2-3 Week Webex)
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Inconsistent answers between Project and Support | One of biggest issues is that the Project team provided advice or instruction on how to do things in ctcLink, but then when working with the Customer Support team, the advice or instruction is completely different. Has led to many errors and mistakes that could’ve been avoided had both sides of that house been in alignment. |  | Pierce | The Project team and Customer Support organization continue to align knowledge and skills.
Cutover confusion | Notification email reminders about cutover job scheduling included all jobs that needed to be run and we received duplicate notifications from different support staff, which created confusion. | Make sure there is a clear understanding of who is running which jobs (Finance, Enrollment Services, etc). | Lower Columbia | Will provide this request to IT.
Account Activation | Our account activation volunteers didn't really know that much about how ctcLink works, but were very eager to help and learn about the system and account activation process. SMEs who knew the most about the system were tied up with other items pre and post go-live, so couldn’t offer account activation or troubleshooting support. | It might be helpful to develop a “Troubleshooting Account Activation 101" course on Canvas for people providing support. | Lower Columbia | Will provide this suggestion to Customer Support

## Slide 25: College suggestions for Transition support (2-3 week webex), cont’d
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Account Activation | We had to roll the system out to students completely remotely. We used a combination of Zoom, email and phones to support account activation for both staff and students (once our in-person labs were no longer possible). Not being able to see their screens (if they are not on Zoom or unable to send screenshots) has made account activation more challenging. | Remote account activation help needed | Lower Columbia | Project team collaborating with SBCTC IT/Customer Support to provide tips, update QRGs as needed.
Account Activation | We would have loved to have a flow chart of common problems and solutions before we started with account activation support. We had identified a handful of potential issues ahead of time and planned for how to resolve them, but overall did not know what a lot of the problems were going to be, of course, several people doing the support ended up with cheat sheets of some sort. | Flow chart of how to resolve common problems, cheat sheets | Lower Columbia | Project Team gathered common issues, tips and tricks from DG3A to support DG3B Tier 1 Support. Will work with SBCTC IT and Customer Support to provide tip sheets and update QRGs as needed.

## Slide 26: Post go-live support
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Orientation to Support for College SMEs | This would build a better relationship and hand-off to support. Some areas of FIN have a smoother hand-off because support resources are highly engaged in earlier project activities with the SMEs. | Suggest an orientation (welcome, virtual meet & greet) prior to go-live (maybe during UAT) and more formal hand-off process. | FIN | We will adjust this methodology for DG4.

## Slide 27: College suggestions for post go-live support
Lessons Learned | Description/Issue | Recommendation | Source | ctcLink PMO Comments
Webex support | Was sometimes frustrating to wait turn for your questions |  | Olympic | We will pass this on to Customer Support.
Be prepared for validation and security issues at Go-Live | If you have the same validation issues or security issues before Go-Live that repeat with each Sprint, know that Go-Live will be similar. | If you have the same validation issues or security issues before Go-Live that repeat with each Sprint, know that Go-Live will be similar. | Lower Columbia | We will pass this on to future DGs.

## Slide 28: Next steps
Meetings | Date Completed
ctcLink PMO Compiled DG3 Lessons Learned Report | July-August 2020
Moran Reviews Draft DG3 Lessons Learned Report | August 2020
Present Final Report to Steering Committee | September 2020
Post Final Report as Deliverable to OCIO Site | September 2020
Share/Post Final Report with Current & Future Deployment Groups | September 2020
DG3 lessons learned Google sheet