## QuickStartGuide
Major Project Report
Quick Start Guide
BACKGROUND INFORMATION
The Final Project Close-out Report requirement was implemented in the 2013-15 biennium as part of the recommendations in the 2009 JLARC report, “Evaluation of the Accuracy of Capital Project Cost Estimates.” This requirement is for agencies to submit the report to OFM at project completion to compare the scope and estimate from the predesign stage with the final scope and actual cost after construction as well as the estimate as the project was funded.
RCW 43.88.160 requires OFM to submit an annual report to the Legislature on the status of all appropriated capital projects (including transportation projects) that show significant cost overruns or underruns. As these projects are completed, agencies must provide OFM with a final summary showing estimated start and completion dates of each project phase compared to actual dates, as well as estimated costs of each phase compared to actual costs. OFM uses the information collected in the Final Project Close-out Report to make its annual report to the Legislature.
Agencies administering a major capital project or projects specifically identified for this reporting requirement by OFM or the Legislature must submit a detailed Major Project Status Report to OFM and the legislative fiscal committees each December 31 and July 1.
GENERAL INFORMATION
This comprehensive reporting tool merges the Major Project Status Report and the Final Project Close-Out Report. This is to generate consistency in reported data as required by OFM, the Legislature, and state statute; especially as it pertains to comparing cost estimates at predesign approval, cost estimates as projects are currently funded, and the actual costs at project completion.
Please contact your assigned OFM Capital Budget Analyst if you have any questions regarding this tool.
INSTRUCTIONS
1) | Blue cells are available for data entry.
2) | Select the type of report you will be submitting in cell B2. Select "Major Project Status Report" if your report is to fulfill the semi-annual requirement to update OFM and the Legislature on the status of your project. Select "Final Project Close-Out Report" if your project is complete.
3) | In the funding section, please include all funding sources for the project by phase. Identify the fund number and name (for example: "06X - Building and Tuition Acct"). Identify all local and alternative funding sources and all OFM authorized transfers from other projects. Insert rows where necessary.
4) | Cost and other variances can be compared three ways: 1) Estimates at Approved Predesign to Estimates as Currently Funded. 2) Estimates at Approved Predesign to Actuals. 3) Estimates as Currently Funded to Actuals). Click on cell H55 to select your variance comparison.
5) | Additional information, such as number and value of change orders, is required for the Final Project Close-Out Report. Those cells will be made available when that report type is selected in cell B2.
6) | If available, photos can be added to the Photo Gallery tab for a visual representation of the status of the project. Pictures can sometimes provide a better understanding of the status of a construction project than one can get from just the schedule or expenses to date. Right-click on the stock photos and select "Change Picture" to insert your photo from a file. Captions of the photo can be made in the text box below the photo.

## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2023-25 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
December 2024
| Agency | 699
| Project Name | Clark College - North County Satellite
| OFM Project Number(s) | 30000135
Contact Information
| Name | Chris Samuels
| Phone Number | 360-992-2408
| Email | csamuels@clark.edu
Project Information
| Project Description: | Designed and constructed under a progressive design-build contract, the new building will serve north Clark County residents through General Education programs and a new Advanced Manufacturing Center (AMC) program including Welding, Machining, Metallurgy, 3D Printing and associated skills development at the new Boschma Farms campus in Ridgefield. Total building area is approximately 50,000 square feet gross. The building includes a computer lab, study spaces, conference rooms, and administrative offices. The 10-acre site has parking lots with electric vehicle charging stations and a new street from the north side of the Pioneer Street roundabout that provides for vehicular entrance, and will also serve future campus expansion across 40 additional acres.
(Include a brief summary of the project and the programs it supports.)
| Project Status: | In March 2019 the Predesign Report recommended construction of a 70,000 GSF building at a total rounded project cost of $54,923,000. The Design-Build selection process concluded with NTP issued in April 2022. Design and construction costs escalated at double-digit annual rates and site development costs were higher than anticipated, forcing reduced building area. The Guaranteed Maximum Price was negotiated in April 2023 and site earthwork began in June. The project is now 100% complete in terms of construction and commissioning activities. Clark College is installing furnishings, fixtures and equipment. Substantial Completion was achieved on September 30, 2024 and Final Completion will be December 31, 2024. To date, the progressive design-build Contract Value has been reduced by ($1,232,811) due to unspent construction contingency and the unused portion of construction allowances. The FF&E installation is currently ongoing and expected to last until Spring of 2025. The project management team is working with local AHJ to obtain the final certificate of occupancy. The anticipated date for this milestone is Feb 2025.
(Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.)
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan |  |  | TOTAL | Notes
| Phase & Fund Type | Prior Expended | 2023-25 Expended | 2023-25 Remaining | 2025-27 Plan | Future Plan
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldg. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 3186525 | 0 | 0 | 0 | 0 | 3186525
| 057 - State Bldg. Const Acct | 3186525 |  | 0 |  |  | 3186525 | U95
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 3188514 | 46616564.16 | 9426384.84 | 0 | 0 | 59231463
| 057 - State Bldg. Const Acct | 3188514 | 46616564.16 | 5926384.84 |  |  | 55731463 | C01
| XXX - Other State Funding | [5 empty] | 0
| 147 - Local Funds | 0 |  | 3500000 |  |  | 3500000 | Q749
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 6375039 | 46616564.16 | 9426384.84 | 0 | 0 | 62417988
Details
| Construction Type | Vocational schools |  | Project Administered By |  | DES
| % of Bldg. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 70000 | 50000 | 50000 | 0 | GSF reduced from Predesign due to cost escalation
| Usable Sq Ft (USF) |  |  | 50250 | 39300 | 39300 | 0
| Space Efficiency (USF/GSF %): |  |  | 71.79% | 78.6% | 78.6% | 0%
| Site Work SF: |  |  | 430000 | 430000 | 430000 | 0
| Demolition SF (provide building names in comments): | [5 empty] | 0 | No demolition
| MACC/Bid Award COST/GSF |  |  | 637.9677 | 834.22 | 904.554 | 70.334
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 726.2797 | 1155.8289 | 1007.1838 | -148.6451
Milestone Dates
| Predesign Complete |  |  | 2019-05-01 | 2019-09-01 | 2019-05-22 |  | OFM approved
| Start Design |  |  | 2021-11-08 | 2022-04-01 | 2022-04-01 | 0 mo.
| Bid Due Date | [6 empty] | Progressive Design Build
| Notice to Proceed |  |  | 2022-05-30 | 2023-06-01 | 2022-04-01
| Substantial Completion |  |  | 2024-08-01 | 2024-09-01 |  |  | 2024-09-30
| Final Acceptance/Project Close-out Date |  |  | 2024-09-01 |  |  | 0 mo. | Predict 12/31/24
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
| Acquisition Costs Total |  |  |  | 13521 | 14118 | 597 | College cost to receive land donation
Consultant Services
| Pre-Schematic Design Services |  |  | 770022 | 376656 | 376656 | 0
| AE Basic Service Fee - Construction Documents |  |  |  | 1 | 207091.4 | 207090.4
| Extra Services - Pre-Bid |  |  | 446956 | 211968 | 10000 | -201968
| AE Basic Service Fee - Bid/Construction/Closeout |  |  |  | 1 |  | -1
| Other Services - Post Bid |  |  | 360660 |  |  | 0
| Design Services Contingency |  |  |  | 1 |  | -1
| Consultant Services Total |  |  | 1577638 | 588627 | 593747.4 | 5120.4
Construction
| Site Work |  |  | 11587825 | 6725827 | 7200000 | 474173
| Related Project Costs |  |  |  | 5891908 | 3500000 | -2391908
| Facility Construction |  |  | 33069916 | 29093265 | 34527700 | 5434435
| Maximum Allowable Construction Cost (MACC) Subtotal |  |  | 44657741 | 41711000 | 45227700 | 3516700
| Construction Contingencies |  |  | 2242241 | 2317925 | 1144528 | -1173397
| Non-Taxable Items | [5 empty] | 0
| Sales Tax |  |  | 3939599 | 4625442 | 3048962 | -1576480
| Design-Build Costs |  |  |  | 6050567 | 938000 | -5112567
[5 empty] | 3086512 |  | -3086512
| Construction Contracts Total |  |  | 50839581 | 57791446 | 50359190 | -7432256
Other Project Costs
| Equipment |  |  | 1664168 | 3307799 | 2070110 | -1237689
| Art Work |  |  | 223289 | 293124 | 56519 | -236605
| Project Management |  |  | 360660 | 423077 | 532625 | 109548
| Other Costs (DES Interagency Agreement, College project management, etc.) |  |  | 257916 |  | 4834 | 4834
| Other Project Costs Total |  |  | 2506033 | 4024000 | 2664088 | -1359912
| Total Project Costs |  |  | 54923252 | 62417594 | 53631143.4 | -8786450.6
Additional comments:
On Dec 2024, Clark College was notified by the WA Arts Commission that Sarah Folden would not be providing her services for curating the exterior art piece. The WA Arts Commission has only committed Ryan Feddersen to curate interior artwork. The artist, WA Arts, and Clark College art committee have walked the building to observe ideal locations for the installation of interior art pieces.

## Photo Gallery
Photo Gallery
Aerial View
Roundabout showing Clark Collge campus
South Elevation
Building Entrance SE Corner
East Elevation
North Elevation & Parking Lot
Aerial View
View of High-bay Shop space
View of High-bay Shop space
View of High-bay Shop space

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | January 2025 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | February 2025
Art galleries |  |  | 2006 | Other (explain below) | March 2025
Auditorium with stage |  |  | 2007-09 |  | April 2025
Auditorium without stage |  |  | 2008 |  | May 2025
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | June 2025
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | July 2025
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | August 2025
Computer rooms |  |  | 2012 |  | September 2025
Convention facilities |  |  | 2013-15 |  | October 2025
Courthouses |  |  | 2014 |  | November 2025
Day care facilities |  |  | 2015-17 |  | December 2025
Detention/correctional facilities - maximum |  |  | 2016 |  | January 2026
Detention/correctional facilities - min & max |  |  | 2017-19 |  | February 2026
Dining halls/institute |  |  | 2018 |  | March 2026
Dormatories |  |  | 2019-21 |  | April 2026
Emergency generator facilities |  |  | 2020 |  | May 2026
Exposition building |  |  | 2021-23 |  | June 2026
Extended care facilities |  |  | 2022 |  | July 2026
Farm structures |  |  | 2023-25 |  | August 2026
Fire and police stations |  |  | 2024 |  | September 2026
Fish hatcheries |  |  |  |  | October 2026
Greenhouses |  |  |  |  | November 2026
Guard towers |  |  |  |  | December 2026
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")